## Surender to be deleted (hidden)
Combined four different resources (links below) in to this workbook
Template: Schedule of activities | 2022-02-14
Example: Financial statements reporting timetable | Green tab 4 - final - all agree
Example: Financial Statements Project Plan | tab2 & 3 to be finalised and consequently tab 1
Checklist: Developing a schedule of activities | updated - walkthrough colour codes on tab 2
June year end 19-20 detailed year end - year convention update
Can you please review this workbook and advise | Ag plan is good and detailed has many entity specific steps - but this guide needs to be generic. Generic steps have been lifted.
whether this makes sense as a whole
mark any amendments/suggestions - activities or tasks left out/doubled up or out of sequence
what further can be left out to make it more efficient/compact or added to make it more meaningful
have a look on the dates - suggest any updates
tab 2 - need to split pre year in hard close specific activities
tab 3 - if I want to convert this to FY 21-22 - where do I pick the dates from ? Or is it better to leave in a dd/mm/yyyy format - that way firstly it is internally consistent (with tab1) and then easily reusable and is low maintenance for us
tab4 - for majority there is a month for some there are specific dates - what is the relevance of them. Is it better to put them as dd/mm format
who else can help/review/add value - Mel suggested KPMG
They look to be repetitive - but target different requirements/situations/stakeholders
on tab 2 - mapping from developing a schedule of activities document - now fully absorbed in this tab
is it correct?

## 1. Foreword
Example: Financial statements schedule of activities/year-end project plan/high level timetable
Foreword
The worksheets in this workbook contain example indicative schedules/timetables to meet different situational needs and should be tailored to meet entity specific requirements. The project manager and/or financial statements team should prepare the schedule of financial statement project activities by making a list of milestones, critical events and significant management issues, and then identify the tasks, responsibilities and timeframes associated with completing these. Consideration should be given to the sequence of activities and the estimated time required for completing each task or activity. This should include the provision of information to, or from, external parties such as shared services providers. Working backwards from the most critical date, which is generally the signing of the financial statements, is often the most effective means of allocating timeframes that support the project delivering on time. Entities should note that the largely sequential nature of many activities and tasks undertaken in the closing process, means that a missed deadline can create a significant delay for the entire process. This could jeopardise the timeliness of the financial statements. Accordingly, timeframes need to be carefully planned, adhered to and regularly monitored and reviewed as needed. The schedule should, to the extent possible, incorporate all aspects of financial reporting for both internal and external purposes. It should be developed so that it can be readily updated each year. In this way, planning builds on the experience from the previous year, taking account of aspects that may be improved. Most importantly, the schedule/s should clearly assign individual responsibilities and indicate timelines for carrying out and completing each task.
Tab 2: Schedule of activities - outlines the tasks to be completed in the preparation process from initial planning through to finalisation, including the timeline and responsibility for the completion of each activity. The plan assumes a hard close at the end of April and a year-end date of 30 June. It is better practice that the day of the week as well as the date be shown in the ‘due date’ column. The example schedule of activities should be modified to meet the entity’s particular circumstances and needs. The plan does not necessarily cover all possible events and actions. Some smaller entities would require less time, if their tasks are less complex. In this example, the audit committee does not rely on a sub committee to review the financial statements process. If your entity's governance arrangements include a sub committee, you would need to include that in your schedule.
Tab 3: Detailed financial statements year-end project plan - outlines the activities to be completed in the financial statements preparation process, including the timeline and responsibilities for the completion of each activity and its status. It provides an example of a year-end project plan and assumes a year-end date of 30 June 2022. It covers only year-end activities and should be supported by detailed planning and hard close activity plans. Again this should be tailored to meet the entity's particular circumstances and needs.
Tab 4: High level timetable - provides a summary timetable of key financial reporting dates, in a form that is convenient for key stakeholders such as an audit committee or the ANAO. As highlighted earlier, the appropriate level of detail is likely to differ between entities, depending on stakeholders’ requirements—some stakeholders may require more or less detail than what is included in this example. This example includes a number of steps, dates, committees and positions that may not be relevant to all entities, for example, an accounting policy manual, hard close, performance and financial statements sub committee, director of financial reporting, secretary, etc. These terms are included to represent the type of information that may be included.

## 2. Schedule of activities
Schedule of activities
Ref | Action required | Due date | Responsibility | Assigned Officer | Completed | Date completed | Comment
FT/BA/FMIS Management issues/actions
1 | Completing monthly reporting requirements | dd/mm/yyyy | FT
2 | Commence financial statements planning. | dd/mm/yyyy | FT |  | Y
3 | Recruiting additional or replacement staff - ensuring the availability of suitably qualified staff including subject matter experts during the close-off process. | dd/mm/yyyy | HR/FT
4 | Implementing system changes and updates | dd/mm/yyyy | FMIS/FT
5 | Assessing the need for legal and accounting advice | dd/mm/yyyy | FT
6 | Communicating with third parties, including shared service providers, valuers, actuaries and solicitors | dd/mm/yyyy | FT
Pre year-end
7 | Consider lessons learned/ANAO recommendations from previous year/s | dd/mm/yyyy | FT
8 | CFO and the ANAO present their schedule of activities, audit strategy, and timetable to the audit committee for discussion. | dd/mm/yyyy | FT/ANAO
9 | CFO presents financial statements risk analysis including major issues impacting the financial statements and acceptable materiality levels for discussion. | dd/mm/yyyy | FT/ANAO
10 | Review of mapping of the financial management information system (FMIS) nominal accounts and reports with financial statements categories. | dd/mm/yyyy | FT
11 | Assets stocktake completed. The stocktake report is prepared for management endorsement and asset register updated. | dd/mm/yyyy | FT
12 | The ANAO commences the interim audit phase. | dd/mm/yyyy | ANAO
13 | Valuation instructions and timetable to be finalised with valuers and actuaries (for example, valuations for non-current assets and estimates of employee entitlements). | dd/mm/yyyy | BA
14 | Prepare position papers on proposed accounting treatments of significant or contentious transactions. | dd/mm/yyyy | FT
15 | Agreement with the audit committee and the ANAO on shell financial statements and proposed accounting treatment of significant or contentious transactions. This action would include identifying opportunities to improve financial statements disclosures. | dd/mm/yyyy | FT/ANAO
16 | Distribution of final information collection pack (including proforma returns) to BA. | dd/mm/yyyy | FT
17 | Information session on the information collection pack. | dd/mm/yyyy | FT
18 | Completion of the mapping of FMIS nominal accounts with the electronic financial statements preparation tool. | dd/mm/yyyy | FT
19 | Actuarial assessment of the salary on-costs (departmental and administered) to be completed. | dd/mm/yyyy | FT
20 | Forward financial instrument notes and variance analysis workbook to BA. | dd/mm/yyyy | FT
21 | Prepare confirmation letters and information requests to third parties (banks, solicitors, and other external stakeholders) and provide to the ANAO for issuance. | dd/mm/yyyy | FT/ANAO
Hard close
22 | Copy of the results of the portable and attractive stocktake, conducted by the business areas, including sign-offs, to FT. | dd/mm/yyyy | BA
23 | Final close in FMIS for 30 April hard close. All revaluation amounts at 30 April to be reflected in FMIS by 30 April. | dd/mm/yyyy | FT/BA
24 | Completion of statement of financial position reconciliations, cash control accounts, assets, employee provisions and Finance’s appropriation system data. | dd/mm/yyyy | FT
25 | Submission of completed returns and financial instrument notes to FT. | dd/mm/yyyy | BA
26 | Submission of 30 April commitments and contingencies register to FT. | dd/mm/yyyy | BA
27 | Submission of variance analysis workbook for 30 April and an analysis of major transactions expected between May and end of June to FT. | dd/mm/yyyy | BA
28 | Submission of statement of financial position reconciliations for 30 April to FT. | dd/mm/yyyy | BA
29 | Completion of working paper folders and preparation of financial statements. | dd/mm/yyyy | FT
30 | Completion of CFO review of working paper folders and draft financial statements. | dd/mm/yyyy | CFO
31 | Distribution of draft financial statements to the audit committee for consideration. | dd/mm/yyyy | FT
32 | Comments on draft financial statements by the audit committee received. | dd/mm/yyyy | FT/AC
33 | Submission of the financial statements for the period ended 30 April to the ANAO, incorporating comments from the audit committee. | dd/mm/yyyy | FT
34 | The ANAO commences audit of the April hard close financial statements, working papers and supporting schedules. A review of significant transactions will also be undertaken. | dd/mm/yyyy | ANAO/FT/BA
35 | Final resolution of all accounting issues with the ANAO. | dd/mm/yyyy | ANAO/FT
36 | CFO, in consultation with the ANAO, to report to the audit committee on matters arising from the interim and hard close process and present any major issues impacting the year-end financial statements. | dd/mm/yyyy | FT/CFO/ANAO
Year-end
37 | All disposals, additions and revaluations of fixed assets to be processed through the fixed assets register in the FMIS by 30 June. The cut-off time for submission of asset journals for year-end processing is 12:00 noon. | Day 0 | BA
38 | FMIS ‘final close’ for Period 12 journals at 6pm. | Day 4 | BA/FT
39 | BAs to assess and reflect movements in valuation of major assets and liabilities between 30 April and 30 June. Supporting documentation to be provided to FT.
40 | Submission of 30 June commitments and contingencies Register to FT. | Day 6 | BA
41 | Submission of completed returns and financial instrument note workbooks for 30 June to FT. Returns are to be submitted by 3:00 pm. | Day 6 | BA
42 | Feedback forms from business managers. | Day 6 | BA
43 | Submission of valuations as at 30 June for non-current assets and superannuation liabilities. | Day 6 | BA
44 | BAs to advise of any material post close off adjustments. | Day 6 | BA
45 | Executive remuneration detail submitted to FT. | Day 7 | HR
46 | Submission of statement of financial position reconciliations for 30 June by 3:00 pm. | Day 7 | BA
47 | Submission of variance analysis workbook for 30 June by 3:00 pm. | Day 7 | BA
48 | Completion of reconciliations including cash, control accounts, assets, employee provisions and Finance’s appropriation system data. | Day 7 | FT
49 | Material adjustments agreed with the ANAO. BAs to be advised of adjustments to be made. | Day 7 | FT/ANAO
50 | Responses to confirmation letters and information requests from third parties due. Follow up on any outstanding requests. | Day 7 | FT
51 | Preparation of draft financial statements. | Day 10 | FT
52 | CFO review of working paper folders and draft financial statements. | Day 10-11 | CFO
53 | Complete quality assurance review. This review could be undertaken with the assistance of internal audit or other areas not directly involved with financial statements preparation. | Day 11–15 | CFO
54 | Distribute first draft of financial statements to the audit committee for consideration. | Day 15 | FT
55 | Comments on financial statements by the audit committee received. | Day 16 | AC
56 | Completion of working paper files and supporting schedules detailing year-end financial statements figures. | Day 17 | FT
57 | Submission of first draft of financial statements to the ANAO. | Day 17 | FT
58 | Valuation reports for non-current assets and actuarial reports for superannuation liabilities to FT. | Day 17 | BA
59 | Submission of management sign-offs and CFO report to the accountable authority and the audit committee. | Day 25 | BA
60 | Final financial statements and supporting schedules as at 30 June completed. | Day 25 | FT
61 | Review the ANAO Closing audit letter/final management letter and provide management comments within agreed timeframes. | Day 25 | CFO/BA
62 | Sign-off of final financial statements for the year ended 30 June by the audit committee. Committee’s recommendation to the accountable authority. Committee’s approval of information for submission to Finance for consolidation. | Day 29 | AC
63 | Completion of representation letter by the accountable authority and CFO. | Day 29 | AA/CFO
64 | Final financial statements for the year ended 30 June submitted to the ANAO. | Day 29 | FT
65 | Final clearance provided by the ANAO. | Day 30 | ANAO
66 | Financial statements signed by the accountable authority and auditor’s report by the ANAO. | Day 32 | ANAO/AA/CFO
67 | Provide audit-cleared information to Finance for its preparation of Australian government consolidated financial statements. | Day 32 | FT
68 | Signed financial statements and auditor’s report (exactly as signed) sent to publications section for inclusion in the annual report. | Day 32 | FT
69 | Reconcile roll over of opening balances in FMIS. | Day 35 | FT
70 | Conduct a lessons learned session. | Day 39 | FT/BA
71 | Obtain feedback from the ANAO. | Day 45 | ANAO/ FT/CFO
KEY | Description
AA | Accountable authority
AC | Audit Committee
ANAO | Australian National Audit Office
BA | Business areas
CFO | Chief Financial Officer
FMIS | Financial Management Information System
FT | Financial statements team or members of the financial statements team
HR | Human Resource Branch
Toolkit

## 3. Jun year end X1-X2 timetable (hidden)
| Manual tracking | Completed |  |  |  | Overdue
|  | WIP |  |  |  | Due for completion
| 20X1-X2 Financial statements project plan | NA
Phase | Task name | Start | Finish | 43502 | Overdue | Status | Comments | Primary resource | Secondary resource | Submitted for review | First review | Edits processed | Manager review | Edits processed2 | Cleared | Additional comments
1. | End of period Activities | 1 June 20X2 | 29 June 20X2
| Follow up outstanding previous HC Issues (if applicable) | 1/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Release 2019-20 EOY timetable | 1/06/20X2 | 15/06/20X2 | #VALUE! | #VALUE!
| Request equity balances from corporate commonwealth entities | 19/06/20X2 | 26/06/20X2 | #VALUE! | #VALUE!
| Send emails reminding of EOY, contingencies, entities | 19/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Follow up AUC balances | 18/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Prepare capital expenditure journals | 18/06/20X2 | 15/07/20X2 | #VALUE! | #VALUE!
| Prepare other monthly journals | 18/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Prepare solicitors' representation letters | 19/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Prepare bank confirmation letters | 15/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Test/post depreciation and settlement | 29/06/20X2 | 2/07/20X2 | #VALUE! | #VALUE!
| Update the FS model with budget information -AASB 1055 | 18/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Update lead schedule templates - departmental | 3/07/20X2 | 9/07/20X2 | #VALUE! | #VALUE!
| Update lead schedule templates - administered | 3/07/20X2 | 9/07/20X2 | #VALUE! | #VALUE!
| PGPA Section 51 (Making amounts appropriated available) process | 22/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
| Update financial statements template | 18/06/20X2 | 29/06/20X2 | #VALUE! | #VALUE!
2. | Systems Processing | 2020-06-29 | 2020-07-06
| Invoices to be processed in FMIS | 25/06/20X2 | 2020-06-26 | 506
| Last payment run for June | 2020-06-30 | 2020-06-30 | 510
| FMIS commitment report | 2020-07-02 | 2020-07-02 | 512
| EOM payroll accrual files for June 2020 | 2020-06-29 | 2020-06-29 | 509
| Close travel module and goods receipt module in FMIS | 2020-06-29 | 2020-06-29 | 509
| Final credit card export for the month | 2020-06-29 | 2020-06-29 | 509
| Close accounts payable | 2020-06-29 | 2020-06-29 | 509
| Close accounts receivable | 2020-07-02 | 2020-07-02 | 512
| Final bank statement processing | 2020-07-02 | 2020-07-02 | 512
| Close June 2020 period in FMIS | 2020-07-02 | 2020-07-02 | 512
| Open July 2020 and period 13 in FMIS | 2020-07-06 | 2020-07-06 | 516
3. | Period 13 activities (N/A) | 2020-07-02 | 2020-07-27
| Reflect equity balances from corporate commonwealth entities in FMIS | 2020-07-02 | 2020-07-20 | 530
| Asset revaluation | 2020-07-02 | 2020-07-20 | 530
|  | 2020-07-17 | 2020-07-27 | 537
4. | Employee leave liabilities | 2020-06-29 | 2020-07-13
| Commencements and terminations reports | 2020-06-29 | 2020-06-30 | 510
| LSL & planned leave taken and superannuation reports | 2020-07-01 | 2020-07-06 | 516
| Overpayments register | 2020-06-29 | 2020-06-29 | 509
| Executive remuneration reports | 2020-07-02 | 2020-07-06 | 516
| Leave liability reconciliations | 2020-07-02 | 2020-07-06 | 516
| Super oncosts journals adjustment to P&L | 2020-07-09 | 2020-07-13 | 523
| Employee provisions - shorthand method | 2020-07-09 | 2020-07-13 | 523
5. | Cash Management sign-off (N/A) | 2020-07-03 | 2020-07-13
| ACM journals | 2020-07-03 | 2020-07-08 | 518
| Departmental ACM sign-off | 2020-07-08 | 2020-07-09 | 519
| Administered ACM sign-off | 2020-07-08 | 2020-07-09 | 519
| EL1 review | 2020-07-09 | 2020-07-10 | 520
| EL2 review | 2020-07-10 | 2020-07-10 | 520
| CFO sign-off | 2020-07-10 | 2020-07-13 | 523
| Deadline to submit to Finance |  | 2020-07-13 | 523
6. | CBMS - monthly actuals | 2020-07-02 | 2020-07-24
| Underlying cash balance - to submit to Finance | 2020-07-02 | 2020-07-02 | 512
| Departmental CBMS reporting & preparation of executive summary | 2020-07-03 | 2020-07-20 | 530
| Administered CBMS reporting & preparation of executive summary | 2020-07-03 | 2020-07-20 | 530
| EL1 review | 2020-07-21 | 2020-07-22 | 532
| EL2 review | 2020-07-22 | 2020-07-23 | 533
| CFO sign-off | 2020-07-23 | 2020-07-24 | 534
| Deadline to submit to Finance |  | 2020-07-27 | 537
7. | Financial statements | 2020-07-03 | 2020-07-23
Draft primary financial statements (week 1)
| Departmental statement of comprehensive income | 2020-07-03 | 2020-07-06 | 516
| Departmental statement of financial position | 2020-07-03 | 2020-07-06 | 516
| Departmental statement of changes in equity | 2020-07-03 | 2020-07-06 | 516
| Departmental cash flow statement | 2020-07-03 | 2020-07-06 | 516
| Administered schedule of comprehensive income | 2020-07-03 | 2020-07-06 | 516
| Administered schedule of assets and liabilities | 2020-07-03 | 2020-07-06 | 516
| Administered reconciliation schedule | 2020-07-03 | 2020-07-06 | 516
| Administered cash flow - Monthly (CBMS) | 2020-07-03 | 2020-07-06 | 516
1. Departmental financial performance
| 1.1: Expenses | 2020-07-06 | 2020-07-10
| 1.1A: Employee benefits | 2020-07-06 | 2020-07-10 | 520
| 1.1B: Supplier expenses (goods and services) | 2020-07-06 | 2020-07-10 | 520
| 1.1B: Other supplier expenses (lease and workers comp) | 2020-07-06 | 2020-07-10 | 520
| 1.1C: Grants | 2020-07-06 | 2020-07-10 | 520
| 1.1D: Finance costs | 2020-07-06 | 2020-07-10 | 520
| 1.1E: Write-down and impairment of assets | 2020-07-06 | 2020-07-10 | 520
*Losses from asset sales
| 1.1F: Other expenses | 2020-07-06 | 2020-07-10 | 520
| Working note depreciation and amortisation | 2020-07-06 | 2020-07-10 | 520
| 1.2: Own-source revenue and gains | 2020-07-06 | 2020-07-10
| 1.2A: Sale of soods and rendering of services | 2020-07-06 | 2020-07-10 | 520
| 1.2B: Rental income | 2020-07-06 | 2020-07-10 | 520
| 1.2C: Other revenue | 2020-07-06 | 2020-07-10 | 520
*Reversals of previous write-downs
| 1.2D: Gains from sales of assets | 2020-07-06 | 2020-07-10 | 520
| 1.2E: Other gains | 2020-07-06 | 2020-07-10 | 520
| 1.2F: Revenue from government | 2020-07-06 | 2020-07-10 | 520
| Working note foreign exchange gains | 2020-07-06 | 2020-07-10 | 520
| 1.3: Other comprehensive income | 2020-07-06 | 2020-07-10
| 1.3: Other comprehensive income | 2020-07-06 | 2020-07-10 | 520
2. Income and expenses administered on behalf of government
| 2.1: Administered - expenses | 2020-07-06 | 2020-07-10
| 2.1A: Suppliers | 2020-07-06 | 2020-07-10 | 520
| 2.1B: Subsidies | 2020-07-06 | 2020-07-10 | 520
| 2.1C: Grants | 2020-07-06 | 2020-07-10 | 520
| 2.1D: Finance costs | 2020-07-06 | 2020-07-10 | 520
| 2.1E: Write-down and impairment of assets | 2020-07-06 | 2020-07-10 | 520
| 2.1F: Payments to corporate commonwealth entities | 2020-07-06 | 2020-07-10 | 520
| 2.1G: Other expenses | 2020-07-06 | 2020-07-10 | 520
| Working note depreciation and amortisation | 2020-07-06 | 2020-07-10 | 520
| 2.2: Administered - income | 2020-07-06 | 2020-07-10
| 2.2A: Sales of goods and rendering of services | 2020-07-06 | 2020-07-10 | 520
| 2.2B: Interest | 2020-07-06 | 2020-07-10 | 520
| 2.2C: Dividend | 2020-07-06 | 2020-07-10 | 520
| 2.2D: Rental income | 2020-07-06 | 2020-07-10 | 520
| 2.2E: Other revenue | 2020-07-06 | 2020-07-10 | 520
| 2.2F: Reversal of write-downs and impairment | 2020-07-06 | 2020-07-10 | 520
| 2.2G: Other gains | 2020-07-06 | 2020-07-10 | 520
| Working note return of prior year administered expenses | 2020-07-06 | 2020-07-10 | 520
3. Departmental financial position
| 3.1: Financial assets | 2020-07-10 | 2020-07-16
| 3.1A: Cash and cash equivalents | 2020-07-10 | 2020-07-16 | 526
| 3.1B: Trade and other receivables | 2020-07-10 | 2020-07-16 | 526
| 3.1C: Other financial assets | 2020-07-10 | 2020-07-16 | 526
3.2: Non-financial assets
| 3.2A: Reconciliation of the opening and closing balances of property, plant and equipment and intangibles | 2020-07-10 | 2020-07-16 | 526
| 3.2B: Other non-financial assets | 2020-07-10 | 2020-07-16 | 526
3.3: Payables
| 3.3A: Suppliers | 2020-07-10 | 2020-07-16 | 526
| 3.3B: Other payables | 2020-07-10 | 2020-07-16 | 526
| 3.3B: Unearned income | 2020-07-10 | 2020-07-16 | 526
3.4: Other provisions
| 3.4: Other provisions | 2020-07-10 | 2020-07-16 | 526
4. Assets and liabilities administered on behalf of government
4.1: Administred - financial assets
| 4.1A: Cash and cash equivalents | 2020-07-10 | 2020-07-16 | 526
| 4.1B: Trade and other receivables | 2020-07-10 | 2020-07-16 | 526
| 4.1C: Other investments | 2020-07-10 | 2020-07-16 | 526
| 4.1D: Other financial assets | 2020-07-10 | 2020-07-16 | 526
4.2: Administered - financial assets
| 4.2B: Reconciliation of the opening and closing balances of property, plant and equipment | 2020-07-10 | 2020-07-16 | 526
| 4.2B: Other non-financial assets | 2020-07-10 | 2020-07-16 | 526
4.3: Administered - payables
| 4.3A: Suppliers | 2020-07-10 | 2020-07-16 | 526
| 4.3B: Grants | 2020-07-10 | 2020-07-16 | 526
| 4.3C: Administered GST payable | 2020-07-10 | 2020-07-16 | 526
| 4.3D: Other payables | 2020-07-10 | 2020-07-16 | 526
4.4: Administered - other provisions
| 4.4A: Other provisions | 2020-07-10 | 2020-07-16 | 526
5. Funding
5.1: Appropriations
| 5.1A: Annual appropriations - departmental | 2020-07-17 | 2020-07-23 | 533
| 5.1A: Annual appropriations - administered | 2020-07-17 | 2020-07-23 | 533
| 5.1B: Unspent annual appropriation - departmental | 2020-07-17 | 2020-07-23 | 533
| 5.1B: Unspent annual appropriation - administered | 2020-07-17 | 2020-07-23 | 533
| 5.1C: Special appropriations - departmental | 2020-07-17 | 2020-07-23 | 533
| 5.1C: Special appropriations - administered | 2020-07-17 | 2020-07-23 | 533
5.2: Special accounts
5.2: Special accounts - departmental
| Special account 1 | 2020-07-17 | 2020-07-23 | 533
| Special account 2 | 2020-07-17 | 2020-07-23 | 533
5.2: Special accounts - administered
| Special account 1 | 2020-07-17 | 2020-07-23 | 533
| Special account 2 | 2020-07-17 | 2020-07-23 | 533
5.3: Regulatory charging summary
| 5.3: Regulatory charging summary | 2020-07-20 | 2020-07-23 | 533
5.4: Net cash appropriation arrangements
| 5.4: Net cash appropriation arrangements | 2020-07-20 | 2020-07-23 | 533
5.5: Departmental cash flow (final)
| 5.5: Departmental cash flow (final) | 2020-07-20 | 2020-07-23 | 533
5.6: Administered - cash flow (final)
| 5.6: Administered - cash flow (final) | 2020-07-20 | 2020-07-23 | 533
5.7: Administered - administered reconciliation table
| 5.7: Administered - administered reconciliation table | 2020-07-20 | 2020-07-23 | 533
6. People and relationships
6.1: Employee provisions
| 6.1A: Employee provisions | 2020-07-16 | 2020-07-20 | 530
| 6.1B: Administered - employee provisions | 2020-07-16 | 2020-07-20 | 530
| 6.2: Key management personnel remuneration | 2020-07-16 | 2020-07-20 | 530
| 6.3: Related party disclosures | 2020-07-16 | 2020-07-20 | 530
7. Managing uncertainties
7.1: Contingent assets and liabilities
| 7.1A: Contingent assets and liabilities | 2020-07-16 | 2020-07-20 | 530
| 7.1B: Administered contingent assets and liabilities | 2020-07-16 | 2020-07-20 | 530
7.2: Financial instruments
| 7.2A: Catorgories of financial instruments | 2020-07-20 | 2020-07-23 | 533
| 7.2B: Fair value of financial instruments | 2020-07-20 | 2020-07-23 | 533
| 7.2C: Credit risk | 2020-07-20 | 2020-07-23 | 533
| 7.2D: Liquidity risk | 2020-07-20 | 2020-07-23 | 533
| 7.2E: Market risk | 2020-07-20 | 2020-07-23 | 533
7.3: Administered - financial instruments
| 7.2A: Categories of financial instruments | 2020-07-20 | 2020-07-23 | 533
| 7.3B: Net gains or losses on financial assets | 2020-07-20 | 2020-07-23 | 533
| 7.3C: Fair value of financial instruments | 2020-07-20 | 2020-07-23 | 533
| 7.3D: Credit risk | 2020-07-20 | 2020-07-23 | 533
| 7.3E: Liquidity risk | 2020-07-20 | 2020-07-23 | 533
| 7.3F: Market risk | 2020-07-20 | 2020-07-23 | 533
8. Other information
8.1: Assets held in trust
| 8.1: Assets held in trust | 2020-07-20 | 2020-07-23 | 533
8.2: Restructuring
| 8.2A: Departmental restructuring | 2020-07-20 | 2020-07-23 | 533
| 8.2B: Administered restructuring | 2020-07-20 | 2020-07-23 | 533
8.3: Budgetary reports and explanations of major variances
| 8.2A: Departmental budgetary reports | 2020-07-20 | 2020-07-23 | 533
| 8.2B: Departmental major budget variances | 2020-07-20 | 2020-07-23 | 533
| 8.2C: Administered budgetary reports | 2020-07-20 | 2020-07-23 | 533
| 8.2D: Administered major budgetary variances | 2020-07-20 | 2020-07-23 | 533
8. | CFO file notes | 2020-07-24 | 2020-08-13 | 554
| Departmental CFO file note | 2020-07-24 | 2020-07-28 | 538
| Administered CFO file note | 2020-07-24 | 2020-07-28 | 538
| EL1 review | 2020-07-28 | 2020-07-29 | 539
| EL2 review | 2020-07-29 | 2020-07-30 | 540
| CFO sign-off | 2020-07-30 | 2020-08-03 | 544
9. | CBMSR - Annual Actuals | 2020-07-24 | 2020-08-13 | 554
| Departmental CBMS reporting & preparation of executive summary | 2020-07-24 | 2020-08-07 | 548
| Administered CBMS reporting & preparation of executive summary | 2020-07-24 | 2020-08-07 | 548
| EL1 review | 2020-08-07 | 2020-08-10 | 551
| EL2 review | 2020-08-10 | 2020-08-11 | 552
| CFO sign-off | 2020-08-11 | 2020-08-13 | 554
| Deadline to submit material clearance to Finance |  | 2020-08-14 | 555
10. | Annual reporting pack (supplementary CFS notes) | 2020-08-03 | 2020-08-17 | 558
| Annual reporting pack (supplementary CFS notes) | 2020-08-03 | 2020-08-10 | 551
| EL1 review | 2020-08-10 | 2020-08-13 | 554
| EL2 review | 2020-08-13 | 2020-08-14 | 555
| CFO sign-off | 2020-08-14 | 2020-08-17 | 558
| Deadline to submit annual reporting pack to Finance |  | 2020-08-17 | 558
11. | Independent review | 2020-08-05 | 2020-08-20 | 561
| Review of financial statements by independent contractor | 2020-08-05 | 2020-08-20 | 561
12. | CFO review | 2020-08-20 | 2020-08-21 | 562
| Review of financial statements by CFO | 2020-08-20 | 2020-08-21 | 562
13. | ANAO audit | 2020-07-24 | 2020-08-28 | 569
| ANAO audit of Entity financial statements | 2020-07-24 | 2020-08-28 | 569
14. | PFS sub-committee |  | 2020-08-31 | 572
| PFSSC Meeting |  | 2020-08-31 | 572
| Audit committee/ PFSSC meeting |  | 2020-09-14 | 586
15. | Annual report | 2019-08-27 | 2020-08-28 | 569
| Draft resources for outcomes table | 2020-07-20 | 2020-07-24 | 534
| Draft financial performance appendix | 2020-07-20 | 2020-07-24 | 534
| Annual report management review | 2020-07-24 | 2020-07-27 | 537
| Checking of first draft of the annual report | 2020-07-24 | 2020-08-03 | 544
| Final resources for outcomes table | 2020-08-25 | 2019-08-27 | 202
| Final financial performance appendix | 2020-08-25 | 2019-08-27 | 202
| Final checking of the annual report | 2019-08-27 | 2020-08-28 | 569
16. | Post year end activities | 2020-08-14 | 2020-09-30 | 602
| Management representation letter | 2020-08-14 | 2020-08-24 | 565
| Secretary sign off | 2020-08-28 | 2020-09-21 | 593
| Review process | 2020-09-01 | 2020-09-30 | 602
ANAO key dates
| Items | Dates |  | #VALUE!
| Terminations and commencements | 2020-07-20
| Final TB and transaction listing | 2020-07-20
| First draft statements and supporting notes | 2020-07-24
| Debtors impairment | 2020-07-24
| Asset movement tables and revaluations | 2020-07-24
| Impairment assessments | 2020-07-24
| Appropriation notes and special accounts | 2020-07-27
| KMP report and disclosures | 2020-08-03
| Cash flow | 2020-08-10
| Budgetary reporting | 2020-08-10
| Financial instruments | 2020-08-20
| Second draft statements and supporting notes | 2020-08-21
| Final statements and supporting notes | 2020-09-11
| Second draft | 2020-08-21
| Third draft | 2020-09-11
Formulas:
Completed = MIN([Completed, row below]:C33)
Completed = MIN([Completed, row below]:[Completed, row below])
Finish = MAX([Finish, row below]:D33)
Finish = MAX([Finish, row below])
Note on B53: Sharma, Surender:

## 3. Financial statements plan
| Manual tracking | Completed |  |  |  | Overdue
|  | WIP |  |  |  | Due for completion
| 2021-22 Financial statements project plan | N/A
Phase | Task name | Start | Finish | 43502 | Overdue | Status | Comments | Primary resource | Secondary resource | Submitted for review | First review | Edits processed | Manager review | Edits processed2 | Cleared | Additional comments
1. | End of period Activities | 2022-06-01 | 2022-07-15
| Follow up outstanding previous hard close issues (if applicable) | 2022-06-01 | 2022-06-29 | 1239
| Release 2021-22 end of year (EOY) timetable | 2022-06-01 | 2022-06-15 | 1225
| Request equity balances from corporate commonwealth entities | 2022-06-16 | 2022-06-27 | 1237
| Send emails reminding of EOY, contingencies, entities | 2022-06-16 | 2022-06-29 | 1239
| Follow up assets under construction (AUC) balances | 2022-06-16 | 2022-06-29 | 1239
| Prepare capital expenditure journals | 2022-06-16 | 2022-07-15 | 1255
| Prepare other monthly journals | 2022-06-17 | 2022-06-29 | 1239
| Prepare solicitors' representation letters | 2022-06-17 | 2022-06-29 | 1239
| Prepare bank confirmation letters | 2022-06-15 | 2022-06-29 | 1239
| Update the financial statements model with budget information - AASB 1055 | 2022-06-17 | 2022-06-29 | 1239
| Update financial statements template | 2022-06-17 | 2022-06-29 | 1239
| PGPA Act - section 51 process (making amounts appropriated available) process | 2022-06-22 | 2022-06-29 | 1239
| Test/post depreciation and settlement | 2022-06-29 | 2022-07-01 | 1241
| Update lead schedule templates - departmental | 2022-07-04 | 2022-07-08 | 1248
| Update lead schedule templates - administered | 2022-07-04 | 2022-07-08 | 1248
2. | Systems Processing | 2022-06-24 | 2022-07-06
| Invoices to be processed in FMIS | 2022-06-24 | 2022-06-27 | 1237
| End of month (EOM) payroll accrual files for June 2022 | 2022-06-29 | 2022-06-29 | 1239
| Close travel module and goods receipt module in FMIS | 2022-06-29 | 2022-06-29 | 1239
| Final credit card export for the month | 2022-06-29 | 2022-06-29 | 1239
| Close accounts payable | 2022-06-29 | 2022-06-29 | 1239
| Last payment run for June | 2022-06-30 | 2022-06-30 | 1240
| FMIS commitment report | 2022-07-04 | 2022-07-04 | 1244
| Close accounts receivable | 2022-07-04 | 2022-07-04 | 1244
| Final bank statement processing | 2022-07-04 | 2022-07-04 | 1244
| Close June 2022 period in FMIS | 2022-07-04 | 2022-07-04 | 1244
| Open July 2022 and period 13 in FMIS | 2022-07-06 | 2022-07-06 | 1246
3. | Period 13 activities (N/A) | 2022-07-01 | 2022-07-20
| Reflect equity balances from corporate commonwealth entities in FMIS | 2022-07-01 | 2022-07-20 | 1260
| Asset revaluation | 2022-07-01 | 2022-07-20 | 1260
4. | Employee leave liabilities | 2022-06-29 | 2022-07-13
| Commencements and terminations reports | 2022-06-29 | 2022-06-30 | 1240
| Overpayments register | 2022-06-29 | 2022-06-29 | 1239
| LSL & planned leave taken and superannuation reports | 2022-07-01 | 2022-07-06 | 1246
| Executive remuneration reports | 2022-07-04 | 2022-07-06 | 1246
| Leave liability reconciliations | 2022-07-04 | 2022-07-06 | 1246
| Super oncosts journals adjustment to profit and loss (P&L) | 2022-07-08 | 2022-07-13 | 1253
| Employee provisions - shorthand method | 2022-07-08 | 2022-07-13 | 1253
5. | Cash Management sign-off (N/A) | 2022-07-05 | 2022-07-12
| Cash Module journals | 2022-07-05 | 2022-07-08 | 1248
| Departmental appropriation balances - Cash Module sign-off | 2022-07-08 | 2022-07-11 | 1251
| Administered appropriation balances - Cash Module sign-off | 2022-07-08 | 2022-07-11 | 1251
| EL1 review | 2022-07-08 | 2022-07-11 | 1251
| EL2 review | 2022-07-08 | 2022-07-12 | 1252
| CFO sign-off | 2022-07-08 | 2022-07-12 | 1252
| Deadline to submit to Finance (TBC) |  | 2022-07-12 | 1252
6. | CBMS - monthly actuals | Friday 1 July 2022 | 2022-07-25
| Underlying cash balance - to submit to Finance (TBC) | 2022-07-01 | 2022-07-01 | 1241
| Departmental CBMS reporting & preparation of executive summary (TBC) | 2022-07-05 | 2022-07-19 | 1259
| Administered CBMS reporting & preparation of executive summary (TBC) | 2022-07-05 | 2022-07-19 | 1259
| EL1 review | 2022-07-19 | 2022-07-20 | 1260
| EL2 review | 2022-07-20 | 2022-07-21 | 1261
| CFO sign-off | 2022-07-21 | 2022-07-25 | 1265
| Deadline to submit to Finance - June monthly statements (TBC) |  | 2022-07-25 | 1265
7. | Financial statements | 2022-07-04 | 2022-07-25
Draft primary financial statements (week 1)
| Departmental statement of comprehensive income | 2022-07-04 | 2022-07-06 | 1246
| Departmental statement of financial position | 2022-07-04 | 2022-07-06 | 1246
| Departmental statement of changes in equity | 2022-07-04 | 2022-07-06 | 1246
| Departmental cash flow statement | 2022-07-04 | 2022-07-06 | 1246
| Administered schedule of comprehensive income | 2022-07-04 | 2022-07-06 | 1246
| Administered schedule of assets and liabilities | 2022-07-04 | 2022-07-06 | 1246
| Administered reconciliation schedule | 2022-07-04 | 2022-07-06 | 1246
| Administered cash flow | 2022-07-04 | 2022-07-06 | 1246
1. Departmental financial performance
| 1.1: Expenses | 2022-07-06 | 2022-07-12
| 1.1A: Employee benefits | 2022-07-06 | 2022-07-12 | 1252
| 1.1B: Supplier expenses (goods and services) | 2022-07-06 | 2022-07-12 | 1252
| 1.1B: Other supplier expenses (lease and workers comp) | 2022-07-06 | 2022-07-12 | 1252
| 1.1C: Grants | 2022-07-06 | 2022-07-12 | 1252
| 1.1D: Finance costs | 2022-07-06 | 2022-07-12 | 1252
| 1.1E: Write-down and impairment of assets | 2022-07-06 | 2022-07-12 | 1252
*Losses from asset sales
| 1.1F: Other expenses | 2022-07-06 | 2022-07-12 | 1252
| Working note depreciation and amortisation | 2022-07-06 | 2022-07-12 | 1252
| 1.2: Own-source revenue and gains | 2022-07-06 | 2022-07-12
| 1.2A: Sale of soods and rendering of services | 2022-07-06 | 2022-07-12 | 1252
| 1.2B: Rental income | 2022-07-06 | 2022-07-12 | 1252
| 1.2C: Other revenue | 2022-07-06 | 2022-07-12 | 1252
*Reversals of previous write-downs
| 1.2D: Gains from sales of assets | 2022-07-06 | 2022-07-12 | 1252
| 1.2E: Other gains | 2022-07-06 | 2022-07-12 | 1252
| 1.2F: Revenue from government | 2022-07-06 | 2022-07-12 | 1252
| Working note foreign exchange gains | 2022-07-06 | 2022-07-12 | 1252
| 1.3: Other comprehensive income | 2022-07-06 | 2022-07-06
| 1.3: Other comprehensive income | 2022-07-06 | 2022-07-06 | 1246
2. Income and expenses administered on behalf of government
| 2.1: Administered - expenses | 2022-07-06 | 2022-07-12
| 2.1A: Suppliers | 2022-07-06 | 2022-07-12 | 1252
| 2.1B: Subsidies | 2022-07-06 | 2022-07-12 | 1252
| 2.1C: Grants | 2022-07-06 | 2022-07-12 | 1252
| 2.1D: Finance costs | 2022-07-06 | 2022-07-12 | 1252
| 2.1E: Write-down and impairment of assets | 2022-07-06 | 2022-07-12 | 1252
| 2.1F: Payments to corporate commonwealth entities | 2022-07-06 | 2022-07-12 | 1252
| 2.1G: Other expenses | 2022-07-06 | 2022-07-12 | 1252
| Working note depreciation and amortisation | 2022-07-06 | 2022-07-12 | 1252
| 2.2: Administered - income | 2022-07-06 | 2022-07-12
| 2.2A: Sales of goods and rendering of services | 2022-07-06 | 2022-07-12 | 1252
| 2.2B: Interest | 2022-07-06 | 2022-07-12 | 1252
| 2.2C: Dividend | 2022-07-06 | 2022-07-12 | 1252
| 2.2D: Rental income | 2022-07-06 | 2022-07-12 | 1252
| 2.2E: Other revenue | 2022-07-06 | 2022-07-12 | 1252
| 2.2F: Reversal of write-downs and impairment | 2022-07-06 | 2022-07-12 | 1252
| 2.2G: Other gains | 2022-07-06 | 2022-07-12 | 1252
| Working note return of prior year administered expenses | 2022-07-06 | 2022-07-12 | 1252
3. Departmental financial position
| 3.1: Financial assets | 2022-07-12 | 2022-07-18
| 3.1A: Cash and cash equivalents | 2022-07-12 | 2022-07-18 | 1258
| 3.1B: Trade and other receivables | 2022-07-12 | 2022-07-18 | 1258
| 3.1C: Other financial assets | 2022-07-12 | 2022-07-18 | 1258
3.2: Non-financial assets
| 3.2A: Reconciliation of the opening and closing balances of property, plant and equipment and intangibles | 2022-07-12 | 2022-07-18 | 1258
| 3.2B: Other non-financial assets | 2022-07-12 | 2022-07-18 | 1258
3.3: Payables
| 3.3A: Suppliers | 2022-07-12 | 2022-07-18 | 1258
| 3.3B: Other payables | 2022-07-12 | 2022-07-18 | 1258
| 3.3B: Unearned income | 2022-07-12 | 2022-07-18 | 1258
3.4: Other provisions
| 3.4: Other provisions | 2022-07-12 | 2022-07-18 | 1258
4. Assets and liabilities administered on behalf of government
4.1: Administred - financial assets
| 4.1A: Cash and cash equivalents | 2022-07-12 | 2022-07-18 | 1258
| 4.1B: Trade and other receivables | 2022-07-12 | 2022-07-18 | 1258
| 4.1C: Other investments | 2022-07-12 | 2022-07-18 | 1258
| 4.1D: Other financial assets | 2022-07-12 | 2022-07-18 | 1258
4.2: Administered - financial assets
| 4.2B: Reconciliation of the opening and closing balances of property, plant and equipment | 2022-07-12 | 2022-07-18 | 1258
| 4.2B: Other non-financial assets | 2022-07-12 | 2022-07-18 | 1258
4.3: Administered - payables
| 4.3A: Suppliers | 2022-07-12 | 2022-07-18 | 1258
| 4.3B: Grants | 2022-07-12 | 2022-07-18 | 1258
| 4.3C: Administered GST payable | 2022-07-12 | 2022-07-18 | 1258
| 4.3D: Other payables | 2022-07-12 | 2022-07-18 | 1258
4.4: Administered - other provisions
| 4.4A: Other provisions | 2022-07-12 | 2022-07-18 | 1258
5. Funding
5.1: Appropriations
| 5.1A: Annual appropriations - departmental | 2022-07-19 | 2022-07-25 | 1265
| 5.1A: Annual appropriations - administered | 2022-07-19 | 2022-07-25 | 1265
| 5.1B: Unspent annual appropriation - departmental | 2022-07-19 | 2022-07-25 | 1265
| 5.1B: Unspent annual appropriation - administered | 2022-07-19 | 2022-07-25 | 1265
| 5.1C: Special appropriations - departmental | 2022-07-19 | 2022-07-25 | 1265
| 5.1C: Special appropriations - administered | 2022-07-19 | 2022-07-25 | 1265
5.2: Special accounts
5.2: Special accounts - departmental
| Special account 1 | 2022-07-19 | 2022-07-25 | 1265
| Special account 2 | 2022-07-19 | 2022-07-25 | 1265
5.2: Special accounts - administered
| Special account 1 | 2022-07-19 | 2022-07-25 | 1265
| Special account 2 | 2022-07-19 | 2022-07-25 | 1265
5.3: Regulatory charging summary
| 5.3: Regulatory charging summary | 2022-07-20 | 2022-07-25 | 1265
5.4: Net cash appropriation arrangements
| 5.4: Net cash appropriation arrangements | 2022-07-20 | 2022-07-25 | 1265
5.5: Departmental cash flow (final)
| 5.5: Departmental cash flow (final) | 2022-07-20 | 2022-07-25 | 1265
5.6: Administered - cash flow (final)
| 5.6: Administered - cash flow (final) | 2022-07-20 | 2022-07-25 | 1265
5.7: Administered - administered reconciliation table
| 5.7: Administered - administered reconciliation table | 2022-07-20 | 2022-07-25 | 1265
6. People and relationships
6.1: Employee provisions
| 6.1A: Employee provisions | 2022-07-18 | 2022-07-20 | 1260
| 6.1B: Administered - employee provisions | 2022-07-18 | 2022-07-20 | 1260
| 6.2: Key management personnel remuneration | 2022-07-18 | 2022-07-20 | 1260
| 6.3: Related party disclosures | 2022-07-18 | 2022-07-20 | 1260
7. Managing uncertainties
7.1: Contingent assets and liabilities
| 7.1A: Contingent assets and liabilities | 2022-07-18 | 2022-07-20 | 1260
| 7.1B: Administered contingent assets and liabilities | 2022-07-18 | 2022-07-20 | 1260
7.2: Financial instruments
| 7.2A: Catorgories of financial instruments | 2022-07-20 | 2022-07-25 | 1265
| 7.2B: Fair value of financial instruments | 2022-07-20 | 2022-07-25 | 1265
| 7.2C: Credit risk | 2022-07-20 | 2022-07-25 | 1265
| 7.2D: Liquidity risk | 2022-07-20 | 2022-07-25 | 1265
| 7.2E: Market risk | 2022-07-20 | 2022-07-25 | 1265
7.3: Administered - financial instruments
| 7.2A: Categories of financial instruments | 2022-07-20 | 2022-07-25 | 1265
| 7.3B: Net gains or losses on financial assets | 2022-07-20 | 2022-07-25 | 1265
| 7.3C: Fair value of financial instruments | 2022-07-20 | 2022-07-25 | 1265
| 7.3D: Credit risk | 2022-07-20 | 2022-07-25 | 1265
| 7.3E: Liquidity risk | 2022-07-20 | 2022-07-25 | 1265
| 7.3F: Market risk | 2022-07-20 | 2022-07-25 | 1265
8. Other information
8.1: Assets held in trust
| 8.1: Assets held in trust | 2022-07-20 | 2022-07-25 | 1265
8.2: Restructuring
| 8.2A: Departmental restructuring | 2022-07-20 | 2022-07-25 | 1265
| 8.2B: Administered restructuring | 2022-07-20 | 2022-07-25 | 1265
8.3: Budgetary reports and explanations of major variances
| 8.2A: Departmental budgetary reports | 2022-07-20 | 2022-07-25 | 1265
| 8.2B: Departmental major budget variances | 2022-07-20 | 2022-07-25 | 1265
| 8.2C: Administered budgetary reports | 2022-07-20 | 2022-07-25 | 1265
| 8.2D: Administered major budgetary variances | 2022-07-20 | 2022-07-25 | 1265
8. | CFO file notes | 2020-08-07 | 2022-08-12 | 1283
| Departmental CFO file note | 2022-07-26 | 2022-07-28 | 1268
| Administered CFO file note | 2022-07-26 | 2022-07-28 | 1268
| EL1 review | 2022-07-28 | 2022-07-29 | 1269
| EL2 review | 2022-07-29 | 2022-08-01 | 1272
| CFO sign-off | 2022-08-01 | 2022-08-03 | 1274
9. | CBMSR - Annual Actuals | 2020-08-07 | 2022-08-12 | 1283
| Departmental CBMS reporting & preparation of executive summary | 2022-07-25 | 2022-08-08 | 1279
| Administered CBMS reporting & preparation of executive summary | 2022-07-25 | 2022-08-08 | 1279
| EL1 review | 2020-08-07 | 2022-08-09 | 1280
| EL2 review | 2020-08-10 | 2022-08-10 | 1281
| CFO sign-off | 2020-08-11 | 2022-08-12 | 1283
| Deadline to submit audit cleared statements to Finance (TBC) |  | 2022-08-15 | 1286
10. | Annual reporting pack (supplementary CFS notes) | 2022-08-03 | 2022-08-17 | 1288
| Supplementary reporting pack (supplementary CFS notes) | 2022-08-03 | 2022-08-10 | 1281
| EL1 review | 2022-08-10 | 2022-08-12 | 1283
| EL2 review | 2022-08-12 | 2022-08-15 | 1286
| CFO sign-off | 2022-08-15 | 2022-08-17 | 1288
| Deadline to submit supplementary reporting pack to Finance (TBC) |  | 2022-08-17 | 1288
11. | Independent review | 2022-08-05 | 2022-08-19 | 1290
| Review of financial statements by independent contractor | 2022-08-05 | 2022-08-19 | 1290
12. | CFO review | 2022-08-19 | 2022-08-22 | 1293
| Review of financial statements by CFO | 2022-08-19 | 2022-08-22 | 1293
13. | ANAO audit | 2022-07-22 | 2022-08-29 | 1300
| ANAO audit of entity financial statements (TBC) | 2022-07-22 | 2022-08-29 | 1300
14. | PFS sub-committee |  | 2022-08-30 | 1301
| PFSSC Meeting |  | 2022-08-30 | 1301
| Audit committee/ PFSSC meeting |  | 2022-09-13 | 1315
15. | Annual report | 2022-07-20 | 2022-08-30 | 1301
| Draft resources for outcomes table | 2022-07-20 | 2022-07-26 | 1266
| Draft financial performance appendix | 2022-07-20 | 2022-07-26 | 1266
| Annual report management review | 2022-07-26 | 2022-07-27 | 1267
| Checking of first draft of the annual report | 2022-07-26 | 2022-08-03 | 1274
| Final resources for outcomes table | 2022-08-24 | 2022-08-26 | 1297
| Final financial performance appendix | 2022-08-24 | 2022-08-26 | 1297
| Final checking of the annual report | 2022-08-29 | 2022-08-30 | 1301
16. | Post year end activities | 2022-08-12 | 2022-09-30 | 1332
| Management representation letter | 2022-08-12 | 2022-08-23 | 1294
| Secretary sign off | 2022-08-24 | 2022-09-21 | 1323
| Provision of final signed financial statements to Finance (TBC) | 2022-09-21 | 2022-09-22 | 1324
| Review process | 2022-09-01 | 2022-09-30 | 1332
ANAO key dates
| Items | Dates |  | #VALUE!
| Terminations and commencements | 2022-07-20
| Final TB and transaction listing | 2022-07-20
| First draft statements and supporting notes | 2022-07-25
| Debtors impairment | 2022-07-25
| Asset movement tables and revaluations | 2022-07-25
| Impairment assessments | 2022-07-25
| Appropriation notes and special accounts | 2022-07-26
| KMP report and disclosures | 2022-08-03
| Cash flow | 2022-08-10
| Budgetary reporting | 2022-08-10
| Financial instruments | 2022-08-19
| Second draft statements and supporting notes | 2022-08-22
| Third draft with final adjustments/ANAO findings | 2022-09-12
| Final statements and supporting notes | 2022-09-14
Formulas:
Completed = MIN([Completed, row below]:C21)
Completed = MIN([Completed, row below]:[Completed, row below])
Finish = MAX([Finish, row below]:D21)
Finish = MAX([Finish, row below])

## 4. High level timetable
Financial reporting timetable for the year ended 30 June 20X2
Timeframe | Task | Responsibility | Status
August | Lessons learnt from previous year’s financial statements/audit process | Financial reporting team | Complete
September | Organise a lessons learnt session to determine areas which require improvement, implement efficiencies and better practice methods.
November | Implement ANAO audit recommendations | Financial reporting team, divisions, management | In progress
Implement any audit recommendations from final management letter/closing report.
November / | ANAO audit planning | ANAO | To be actioned
December | ANAO conduct audit planning work and issue engagement letter and audit strategy document.
February | Stocktake | Financial reporting team, finance officers in state offices | To be actioned
Undertake the annual fixed asset and portable and attractive stocktake and valuation work.
XX/February | Financial statements sub-committee (FSSC) | CFO, director financial reporting, FSSC | To be actioned
First meeting for the year to agree on the financial statement timetable and key issues and risks.
February/March | Accounting Standards and PGPA Act Changes | Financial reporting team | To be actioned
Review changes to Australian Accounting Standards (AAS) to assess the impacts on the financial statements for the coming years.
Review changes to the PGPA Act and rules to assess the impacts on the entity’s financial statements for the coming years.
February/March | Position/issues papers | Financial reporting team, Management | To be actioned
Prepare position/issues papers for consultation and agreement with the ANAO covering any issues arising from the interim and hard close processes .
March | ANAO interim audit work | ANAO | To be actioned
ANAO to conduct interim audit fieldwork in December-February.
Expect to receive:
· interim management letter to the Secretary
· interim report to the minister
· interim report to the Parliament.
March | PRIMA draft | Financial reporting team | To be actioned
Review changes to the Finance reporting rules (FRR) and PRIMA to assess the impacts on the agency’s financial statements for the coming years.
March | Develop a timetable for hard close | Financial reporting team | To be actioned
Develop a timetable for the hard close based on CFO time requirements.
March | Prepare for hard close | Financial reporting team, human resources team, divisions, legal team | To be actioned
Organise reports, contracts etc. which will be incorporated into or used in the preparation of the hard close financial statements.
March/April | Asset valuation | Financial reporting team and valuation expert | To be actioned
Finalise the stocktake and update asset register for results and revaluation.
April | Update the accounting policy manual | Financial reporting team | To be actioned
Incorporate the changes to the AAS, PGPA Act, and FRR into the accounting policy manual.
April/May | Conduct hard close | Financial reporting team, Management | To be actioned
Prepare hard close financial statements and notes in accordance with timetable.
May | Update timetable for end of year process | Financial reporting team | To be actioned
Update timetable based on hard close and CFO time requirements.
May | ANAO conduct audit of hard close | ANAO | To be actioned
ANAO to conduct hard close audit fieldwork.
May/June | Financial statements sub-committee | CFO, director financial reporting, FSSC | To be actioned
Discuss the results of April hard close and interim audit, agree appropriate treatment of any accounting issues that have been identified.
June | ANAO feedback on hard close financial statements | ANAO | To be actioned
ANAO to provide feedback on the April hard close financial statement and disclosures.
June | Prepare for end of year | Financial reporting team, human resources team, divisions, legal team | To be actioned
Organise reports, contracts etc. which will be incorporated into or used in the preparation of the year-end financial statements.
July | Prepare outstanding position papers | Financial reporting team | To be actioned
Prepare position/issues papers for consultation and agreement with the ANAO covering any issues arising since the hard close.
July/August | Conduct financial statement process | Financial reporting team | To be actioned
Prepare financial statements and notes in accordance with timetable.
July/August | ANAO final audit | ANAO | To be actioned
ANAO to conduct final audit fieldwork.
August/TBD | ANAO material clearance | ANAO | To be actioned
ANAO to finalise audit and provide material clearance.
XX/August | Financial statements sub-committee | CFO, director financial reporting, FSSC | To be actioned
Conduct detailed review of the annual financial statements.
15 / 31 August | Submit annual actuals to Department of Finance | Financial reporting team, management | To be actioned
Submit materially cleared financial statements to the Department of Finance.
August | Audit report | ANAO | To be actioned
ANAO to finalise audit and provide the audit report. Other receivables from the ANAO include:
· final management letter to the Secretary; and
· closing letter on results of financial statements audit.
XX/August | Financial statements sub-committee | CFO, director financial reporting, FSSC | To be actioned
Audit committee to recommend that the 20X1-X2 financial statements be signed by the accountable authority.
XX/August | Accountable authority to sign 20X1-X2 financial statements | CFO, Secretary | To be actioned
Acronyms and abbreviations
Acronym/abbreviation | Title in full
AAI | Accountable Authority Instructions
AAO | Administrative Arrangements Order
AAS | Australian Accounting Standards as issued by the AASB
AASB | Australian Accounting Standards Board
ANAO | Australian National Audit Office
CFO | Chief Financial Officer
FRR | Public Governance, Performance and Accountability (Financial Reporting) Rule 2015
FSSC | Financial statements sub-committee
MoG | Machinery of Government
PBS | Portfolio Budget Statements
PGPA Act | Public Governance, Performance and Accountability Act 2013
PRIMA | Primary Reporting and Information Management Aid
SRP | Supplementary Reporting Pack
The Budget | The Australian Government budget