## Schedule MoG
Plan Key:
Machinery of Government changes implementation - key dates and common tasks | [18 empty] | Task planned timeframe | [92 empty] | Task not yet started
[18 empty] | w | Task completion date | [92 empty] | In progress
[18 empty] | w | Key date | [92 empty] | In progress with some issues
[7 empty] | Week/ | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | Completed
Task no | Task Group | Sub task | Issue | Activity | Timeframe | Area Responsible | Responsible Officer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | [39 empty] | Task Status | Issues/Notes
1 | Planning, governance and due diligence | Planning | Scoping the MoG change | The Department of the Prime Minister and Cabinet (PM&C) will advise affected entities, the Australian Public Service Commission (APSC) and the Department of Finance (Finance) of the Machinery of Government (MoG) change and its scope. | Day 1 | PM&C | bar: 1
1.01 | Planning, governance and due diligence | Planning | Scoping the MoG change | Affected entities, PM&C, APSC and Finance confirm a common understanding of the scope of the MoG change. | Day 1 | PM&C, APSC, Finance and affected entities | bar: 1
1.02 | Planning, governance and due diligence | Planning | Scoping the MoG change | For large/complex MoGs affecting many entities, PM&C, APSC and Finance meet to agree on milestones for the MoG change. | Day 1 | PM&C, APSC, Finance | bar: 1 to 3
1.03 | Planning, governance and due diligence | Planning | Scoping the MoG change | Legal teams in both entities review the scope of the MoG change and confirm that the change to the Administrative Arrangements Order (AAO) (if made) is sufficient to transfer responsibility for Special Appropriations and Special Accounts. | Day 1 | Legal teams - affected entities | bar: 1 to 2
1.04 | Planning, governance and due diligence | Planning | Initial meeting with affected entities | For large/complex MoGs affecting many entities, Finance will contact affected entities' CFOs to organise a meeting with affected entities' CFOs, PM&C and APSC. For other MoGs, affected entities should establish contact with Finance, the APSC and other entities as appropriate to their respective areas of responsibility. | 3 Days | Finance | bar: 2 to 3
1.05 | Planning, governance and due diligence | Planning | Initial meeting with affected entities | For large/complex MoGs affecting many entities only, initial meeting between affected entities' CFOs, PM&C, APSC and Finance to discuss the MoG and key milestones. | 3 Days | PM&C, APSC, Finance and both entities CFOs | bar: 2 to 3
1.06 | Planning, governance and due diligence | Planning | MoG Steering Committee | Agree on the Terms of Reference for the MoG Steering Committee. |  | CFOs - both entities
1.07 | Planning, governance and due diligence | Planning | MoG Steering Committee | Agree on the membership of the MoG Steering Committee. |  | CFOs - both entities
1.08 | Planning, governance and due diligence | Planning | MoG Steering Committee | Agree on the lines of responsibility and reporting requirements for the MoG Steering Committee. |  | CFOs - both entities
1.09 | Planning, governance and due diligence | Planning | MoG Steering Committee | Agree on the dispute resolution mechanisms for the MoG Steering Committee. |  | CFOs - both entities
1.1 | Planning, governance and due diligence | Planning | MoG Steering Committee | Agree on the meeting schedule for the MoG Steering Committee. |  | CFOs - both entities
1.11 | Planning, governance and due diligence | Planning | Key milestones | Agree key milestones for the MoG change and resource requirements. |  | PM&C, APSC, Finance and both entities CFOs
1.12 | Planning, governance and due diligence | Planning | Transfer protocols | Agree transfer protocols between the transferring and receiving entities for employees, assets, liabilities, appropriations and Average Staffing Level (ASL). |  | CFOs - both entities
1.13 | Planning, governance and due diligence | Planning | Costing protocols | Agree costing/departmental cost allocation principles between the transferring and receiving entities. |  | CFOs - both entities
1.14 | Planning, governance and due diligence | Planning | Implementation plans | Develop project plan and detailed task lists. |  | Project officer - both entities
1.15 | Planning, governance and due diligence | Planning | Implementation plans | Endorsement of implementation plans from the MoG Steering Committee. |  | MoG Steering Committee
1.16 | Planning, governance and due diligence | Planning | Contact lists | Establish a key contacts list, including emails and phone numbers within affected entities, PM&C, APSC and Finance. |  | Project officer - both entities
1.17 | Planning, governance and due diligence | Planning | Date of transfer | Agree a date for departmental appropriation transfers, considering the impacts of public service pay dates and end of month processes. |  | CFOs - both entities
1.18 | Planning, governance and due diligence | Planning | MoG Steering Committee | Hold regular meetings (possibly weekly) of the MoG Steering Committee and report to affected entitles. |  | MoG Steering Committee
1.19 | Planning, governance and due diligence | Planning | Project Transition Office | Agree resourcing requirements, governance, monitoring, dispute resolution protocols and reporting requirements (including reporting format and timing) for the Project Transition Office to provide to the MoG Steering Committee. |  | CFOs - both entities
1.2 | Planning, governance and due diligence | Planning | Responsibility for costs | Agree that responsibility for the costs of implementing the MoG change will be shared between the affected entities. |  | CFOs - both entities
1.21 | Planning, governance and due diligence | Planning | Independent Advisor | Consider whether the MoG is sufficiently complex, material or sensitive to warrant the engagement of an Independent Advisor. Recommend to the Agency Heads of affected entities the appointment of an Independent Advisor. |  | MoG Steering Committee | bar: 11 to 15
1.22 | Planning, governance and due diligence | Planning | Independent Advisor | Agree that an Independent Advisor is required. |  | Agency Heads - both entities | bar: 11 to 15
1.23 | Planning, governance and due diligence | Planning | Independent Advisor | Select an Independent Advisor and agree on the scope of work and the length or engagement for the Independent Advisor. |  | MoG Steering Committee
1.24 | Planning, governance and due diligence | Planning | Independent Advisor | Agree to the engagement of the Independent Advisor recommended by the MoG Steering Committee. |  | Agency Heads - both entities
1.25 | Planning, governance and due diligence | Planning | Independent Advisor | Appoint Independent Advisor. |  | Agency Heads - both entities | bar: 16 to 20
1.26 | Planning, governance and due diligence | Planning | Independent Advisor | Brief the incoming Independent Advisor and provide due diligence information. |  | MoG Steering Committee
1.27 | Planning, governance and due diligence | Due Diligence | Enterprise Agreement | Provide receiving entity with a copy of the transferring entity's current enterprise agreements. |  | Project officer - transferring entity
1.28 | Planning, governance and due diligence | Due Diligence | Enterprise Agreement | Undertake a comparison of the transferring and receiving entitles' enterprise agreements. |  | Project officer - receiving entity
1.29 | Planning, governance and due diligence | Due Diligence | Security clearances | Compare security clearances held for transferring function to clearance level required by receiving entity as a condition of employment. |  | Project officer - transferring entity
1.3 | Planning, governance and due diligence | Due Diligence | Organisational Structure | Provide receiving entity with a copy of the current organisational structure for the transferring function showing reporting lines by Division, Branch, Section and positions and levels, including position vacancies. |  | Project officer - transferring entity
1.31 | Planning, governance and due diligence | Due Diligence | Freedom of information (FOI) requests | Identify all active FOI requests relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.32 | Planning, governance and due diligence | Due Diligence | Induction | Determine the induction needs of transferring employees. |  | Human resources - receiving entity
1.33 | Planning, governance and due diligence | Due Diligence | Induction | Provide induction training if required. |  | Human resources - receiving entity
1.34 | Planning, governance and due diligence | Due Diligence | Induction | Ensure all transferred employees complete accreditation and security clearance upgrade packs as required. |  | Human resources - receiving entity
1.35 | Planning, governance and due diligence | Due Diligence | Risk management plan | Conduct a risk analysis on the functions transferring in. |  | Corporate - receiving entity
1.36 | Planning, governance and due diligence | Due Diligence | Risk management plan | Update risk management plan to reflect the transfer of the affected function. |  | Corporate - both entities
1.37 | Planning, governance and due diligence | Due Diligence | Transfer of information assets | Agree on the process for the transfer or duplication of information assets. |  | CFOs - both entities
1.38 | Planning, governance and due diligence | Due Diligence | Legislative basis for programs | Confirm the legislative basis of the function being transferred and provide copies to the receiving entity. Seek legal advice if required. |  | Project officer - both entities
1.39 | Planning, governance and due diligence | Due Diligence | Secondary and related bodies | Consult the Australian Government Organisations Register (AGOR), to assist in identifying secondary and related bodies that may need to be transferred and advise receiving entity. Update the AGOR dataset, Appointments (Senate Order 15) and Directory contacts held by the Organisation and Appointments Register (OAR) system which is used to publish content on the front facing website known as directory.gov.au. |  | Project officer - both entities
1.4 | Planning, governance and due diligence | Due Diligence | Funding agreements | Identify all active funding agreements relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.41 | Planning, governance and due diligence | Due Diligence | Section 83 of the Constitution assessments | Identify all section 83 assessments relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.42 | Planning, governance and due diligence | Due Diligence | Section 83 of the Constitution assessments | Consider probable impacts arising from risk assessments and the Financial Framework (Supplementary Powers) Act 1997 for the receiving entity. |  | CFOs and Legal Counsels - both entities
1.43 | Planning, governance and due diligence | Due Diligence | Partnerships | Identify all active partnership agreements relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.44 | Planning, governance and due diligence | Due Diligence | Joint ventures | Identify all active joint venture agreements relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.45 | Planning, governance and due diligence | Due Diligence | Leases | Identify all active lease agreements relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.46 | Planning, governance and due diligence | Due Diligence | Memorandum of Understanding (MOU) | Identify all active MoUs relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.47 | Planning, governance and due diligence | Due Diligence | Licences | Identify all licences relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.48 | Planning, governance and due diligence | Due Diligence | Taxation | Confirm all active tax rulings and issues being resolved with the Australian Taxation Office (ATO) relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.49 | Planning, governance and due diligence | Due Diligence | Delegations and Authorities | Identify all active delegations and authorities and provide copies to the receiving entity. |  | Project officer - transferring entity
1.5 | Planning, governance and due diligence | Due Diligence | Assets | Identify all assets (including assets held in trust) relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.51 | Planning, governance and due diligence | Due Diligence | Bank Accounts | Identify all bank accounts (including trust accounts) relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.52 | Planning, governance and due diligence | Due Diligence | Liabilities | Identify all liabilities relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.53 | Planning, governance and due diligence | Due Diligence | Liabilities | Agree protocols for payment of payables outstanding at MoG date of effect. |  | Management Accounting
1.54 | Planning, governance and due diligence | Due Diligence | Credit cards | Identify all credit cards held by employees identified to transfer and provide details to the receiving entity. Obtain a credit card listing and details of limits. |  | Project officer - transferring entity
1.55 | Planning, governance and due diligence | Due Diligence | Official Travel | Identify all current and planned official travel relevant to the transferring function and provide details to the receiving entity. |  | Corporate - transferring entity
1.56 | Planning, governance and due diligence | Due Diligence | Official Passports | Identify all official passports held by employees identified to transfer and provide details to the receiving entity. |  | Project officer - transferring entity
1.57 | Planning, governance and due diligence | Due Diligence | Comparison of accounting policies | Receiving entity to review accounting treatments and assumptions applied to transferring functions (such as capitalisation thresholds, depreciation rates and doubtful debt policies) to ensure they are consistent with those applied by the receiving entity. |  | Project officer - receiving entity
1.58 | Planning, governance and due diligence | Due Diligence | Contracts | Identify all active contracts relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.59 | Planning, governance and due diligence | Due Diligence | Legal Actions | Identify all active legal actions relevant to the transferring function and provide copies to the receiving entity. |  | Project officer - transferring entity
1.6 | Planning, governance and due diligence | Due Diligence | Legal Actions | Agree whether ongoing legal actions will remain with the transferring entity or transfer to the receiving entity. |  | Project officer - transferring entity
1.61 | Planning, governance and due diligence | Due Diligence | Audits | Identify any outstanding audit findings/recommendations, and unfinished or future audits relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.62 | Planning, governance and due diligence | Due Diligence | Employees | Identify the employees and the employee profile (including level, actual salary and allowances) relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.63 | Planning, governance and due diligence | Due Diligence | Employees | Provide details of any employees identified to transfer that are being case managed and employees with active workers compensation claims to the receiving entity. |  | Project officer - transferring entity
1.64 | Planning, governance and due diligence | Due Diligence | Ongoing recruitment actions | Provide details of any ongoing recruitment actions that affect the function identified to transfer the receiving entity. |  | Project officer - transferring entity
1.65 | Planning, governance and due diligence | Due Diligence | Insurance claims | Provide details of any outstanding insurance claims that affect the function identified to transfer to the receiving entity. |  | Project officer - transferring entity
1.66 | Planning, governance and due diligence | Due Diligence | Annual Appropriations | Identify current and prior year annual appropriations and forward estimates (departmental and administered) relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.67 | Planning, governance and due diligence | Due Diligence | Special Appropriations | Identify current year special appropriations and forward estimates relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.68 | Planning, governance and due diligence | Due Diligence | Special Accounts | Identify current special account balances and forward estimates relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.69 | Planning, governance and due diligence | Due Diligence | Own Source Revenue | Identify current and prior year available own source revenue balances and forward estimates relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.7 | Planning, governance and due diligence | Due Diligence | Draft Legislation or Legislation before Parliament | Identify any draft legislation or legislation currently before Parliament which is relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.71 | Planning, governance and due diligence | Due Diligence | Cost Recovery Arrangements | Identify details of cost recovery arrangements relevant to the transferring function and provide details to the receiving entity, including copies of the Cost Recovery Impact Statements. |  | Project officer - transferring entity
1.72 | Planning, governance and due diligence | Due Diligence | Other Commitments | Identify any other commitments relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.73 | Planning, governance and due diligence | Due Diligence | Corporate services | Determine whether the method of delivering corporate services will change, such as early adoption of shared services follow the MoG change or change in provider. |  | Project officer - affected entities
1.74 | Planning, governance and due diligence | Due Diligence | Shared Services | If it is decided that the method of delivering corporate services will change, such as adoption of shared services, the receiving entity should contact the shared services provider entity. |  | Project officer - receiving entity
1.75 | Planning, governance and due diligence | Due Diligence | Shared Services | If an entity has already adopted shared services, contact the shared services provider entity to discuss the impact of the MoG change on the level of services provided and revision/replacement of the MoU for Shared Services. |  | CFO - receiving entity
1.76 | Planning, governance and due diligence | Due Diligence | Grants Hub | Determine whether the method of delivering grants programs will change, such as adoption of the Grants Hub model following the MoG change. |  | CFO - receiving entity
1.77 | Planning, governance and due diligence | Due Diligence | Grants Hub | If a transferring program is being delivered via a Grants Hub and the MoG change will result in an change of Grants Hub provider, the receiving entity should contact the Grants Hub providers and negotiate the transfer. |  | CFO - receiving entity
1.78 | Planning, governance and due diligence | Due Diligence | Ministerial and departmental correspondence | Develop a list of current or outstanding ministerial and departmental correspondence relevant to the transferring function. |  | Project officer - transferring entity
1.79 | Planning, governance and due diligence | Due Diligence | Additional information requirements | Develop a list of additional information requirements. |  | CFO - receiving entity
1.8 | Planning, governance and due diligence | Due Diligence | Parliamentary inquiries and committees | Identify any outstanding recommendations, and unfinished or future inquiries/committee hearings relevant to the transferring function and provide details to the receiving entity. |  | Project officer - transferring entity
1.81 | Planning, governance and due diligence | Due Diligence | Trusts | Identify all trust arrangements relevant to the transferring function and provide details to the receiving entity (include copies of trust deeds or other written agreements). |  | Project officer - transferring entity
1.82 | Planning, governance and due diligence | Governance | Identifying Contentious Issues | Agree that an issue cannot be resolved and advise PM&C, APSC and Finance. |  | Agency Heads
1.83 | Planning, governance and due diligence | Governance | Independent Advisor | Agree that an Independent Advisor is required. |  | Agency Heads
1.84 | Planning, governance and due diligence | Governance | Independent Advisor | Agree on a scope of work for the Independent Advisor and engage a suitable person. |  | Agency Heads
1.85 | Planning, governance and due diligence | Governance | Independent Advisor | Independent Advisor analyses relevant information and reports to agency heads. |  | Independent Advisor
1.86 | Planning, governance and due diligence | Governance | Dispute Resolution Committee | If the matter cannot be resolved and meeting the completion date is in doubt, the Dispute Resolution Committee considers a recommendation by the Independent Advisor and reaches a decision. |  | Dispute Resolution Committee (PM&C, Finance and APSC)
1.87 | Planning, governance and due diligence | Governance | Dispute Resolution Committee's Decision | The Secretary of PM&C (as Chair of the Dispute Resolution Committee) will advise the affected agency heads of the Dispute Resolution Committee's decision in writing. |  | Secretary - PM&C
1.88 | Planning, governance and due diligence | Governance | Development of Communications Strategy | The receiving and transferring entities develop a joint communications strategy and supporting material, including updates to websites and publications. |  | Project officer - both entities
1.89 | Planning, governance and due diligence | Governance | Communications Manager | The Steering Committee should consider appointing a Communications Manager in each affected entity. |  | MoG Steering Committee
1.9 | Planning, governance and due diligence | Governance | Communications Manager | The Steering Committee should agree on a scope of work for the Communications Manager. |  | MoG Steering Committee
1.91 | Planning, governance and due diligence | Governance | Communications Plan | The Steering Committee should agree a joint Communications Plan developed by the Communications Managers from the affected entities. |  | MoG Steering Committee
1.92 | Planning, governance and due diligence | Governance | Initial briefing of employees affected by MoG Change | Shortly after the MoG is announced, affected entities should brief affected employees on the reasons for the MoG change, the scope of the MoG change, support available for them within the entity and how the entity will consult and communicate with them during implementation of the MoG change. A message to all employees may also be appropriate. | Day 3 | Agency Heads /Head of HR /Communications Manager
1.93 | Planning, governance and due diligence | Governance | Frequently Asked Questions | Prepare frequently asked questions and circulate to affected employees. |  | Communications Team - affected entities
1.94 | Planning, governance and due diligence | Governance | Updating employees on MoG process | Affected entities regularly update employees and update frequently asked questions at least weekly during the implementation of the MoG change. |  | Communications Team - affected entities
1.95 | Planning, governance and due diligence | Governance | Update corporate plan | Review corporate plan and update for transferred functions. |  | Corporate - both entities
1.96 | Planning, governance and due diligence | Reporting | Initial report on implementation | CFOs advise PM&C, Finance and APSC of their progress towards meeting the completion date. | Week 4 | CFOs - both entities | bar: 16 to 20
1.97 | Planning, governance and due diligence | Reporting | Third report on implementation | CFOs advise PM&C, Finance and APSC of their progress towards meeting the completion date. | Week 12 | CFOs - both entities | bar: 56 to 60
1.98 | Planning, governance and due diligence | Reporting | Second report on implementation | CFOs advise PM&C, Finance and APSC of their progress towards meeting the completion date. | Week 8 | CFOs - both entities | bar: 36 to 40
2 | People management and pay and conditions | APSC | APSC | For advice on terms and conditions please contact the APSC. Changes to industrial arrangements resulting from the MoG must be consistent with the Government's prevailing workplace relations policy. This may include seeking approval for transitional instruments from the APS Commissioner, as advised by the APSC. Engaging early with the APSC is necessary. | Week 1 | Various - both entities | bar: 1 to 5
2.01 | People management and pay and conditions | Moving employees | APSC | For advice and template determinations to move employees, contact APSC. | Week 1 | Various - both entities | bar: 1 to 5
2.02 | People management and pay and conditions | Moving employees | APSC | Provide employee lists to APSC for check against APS Employment Database (APSED). | Week 11 | Various - both entities | 7 days from moving | bar: 51 to 60
2.03 | People management and pay and conditions | Moving employees | APSC | Provide draft determination to APSC. | Week 12 | Various - both entities | 7 days from moving | bar: 56 to 60
2.04 | People management and pay and conditions | Moving employees | APSC | Provide confirmation of agreement of employee lists from both entities to APSC. | Week 12 | Various - both entities | 2 days from moving | bar: 56 to 60
3 | Delegations and AAIs | Delegations and AAIs | Review of AAIs and delegations | Both entities review delegation instruments and AAIs to ensure they cover the function being transferred and legislation to be administered by that entity. | Day 1 | CFOs - both entities | bar: 1
3.01 | Delegations and AAIs | Delegations | Creation of new delegations | Create new instruments of delegation if required. | Day 1 | CFOs - both entities | bar: 1
3.02 | Delegations and AAIs | Delegations | Interim delegations | The accountable authority of the receiving entity to provide delegations to officials in the transferring entity to enable them to continue to administer functions, until officials in the receiving entity are ready to take over that role. | Day 1 | Agency head / CFO - receiving entity | bar: 1
3.03 | Delegations and AAIs | Delegations | Amend delegations and AAIs | Transferring entity to amend delegations and AAIs to remove delegations if required. | Week 2 | Corporate - transferring entity | bar: 10 to 14
3.04 | Delegations and AAIs | Delegations | Statutory delegations | Review Finance Minister's delegations (PGPA Act) and any other delegations under other legislation or statutory authorisations and amend or seek new delegations as required. | Day 1 | Corporate - receiving entity | bar: 1
3.05 | Delegations and AAIs | Delegations | Third party access arrangements - Cash Management Module of CBMS | Review third party access and amend as required. |  | CFO Group - both entities
3.06 | Delegations and AAIs | Delegations | Third party access arrangements - Cash Management Module of CBMS | Provide updated delegations and third party access arrangements to CFO for approval. |  | CFO Group - both entities
3.07 | Delegations and AAIs | Delegations | Third party access arrangements - Cash Management Module of CBMS | Obtain CFO sign-off on third party access arrangements. |  | CFO Group - both entities
3.08 | Delegations and AAIs | Delegations | Amend delegations and AAIs | Obtain accountable authority's approval for delegations and amended AAIs. |  | Corporate - both entities
3.09 | Delegations and AAIs | Delegations | Train employees on revised AAIs and third party access | Employee training and communication on changes to third party access and AAIs. |  | Corporate - receiving entity
3.1 | Delegations and AAIs | Delegations | Operational guidelines | Update operational guidelines if required. |  | Corporate - both entities
4 | Outcome statements | Outcome Statements | Review of outcome statements | Both affected entities to review their outcome statements to determine if new or amended outcome statement/s are required. | Day 1 | CFO Group - both entities | bar: 1
4.01 | Outcome statements | Outcome Statements | Revision of outcome statements for the receiving entity | If the receiving entity considers that the transferring function is not covered by their existing outcome statement/s they should contact their legal area and Finance urgently for assistance. | Day 1 | CFO Group - receiving entity | bar: 1
4.02 | Outcome statements | Outcome Statements | Revision of outcome statements for the transferring entity | If the transferring entity considers that their existing outcome statements should be changed to reflect their activities after the MoG change, they should contact Finance for assistance and follow the Outcomes Policy Approval process on the Finance website. |  | CFO Group - transferring entity
5 | Information technology | Business systems | Affected business systems | Identify which business systems (if any) need to transfer or be duplicated by the receiving entity. |  | IT Services - transferring entity
5.01 | Information technology | Business systems | Continuity of service delivery | Agree on a method to ensure service delivery while systems are transferred. This may involve the transferring entity continuing to operate the systems while they are transferred. |  | MoG Steering Committee
5.02 | Information technology | Assets | Continuity of service delivery | Agree on a timeframe for the transfer of systems and hardware. |  | MoG Steering Committee
5.03 | Information technology | Business systems | Hardware requirements | Determine whether additional hardware will need to transfer to support transferring business systems. |  | IT Services - receiving entity
5.04 | Information technology | Business systems | Licenses | Transfer affected licenses and software to receiving entity and advise licence provider. |  | IT Services - both entities
5.05 | Information technology | Assets | Transfer of assets | Physically transfer systems and hardware. |  | IT Services - both entities
5.06 | Information technology | Financial Management Information System (FMIS) Data | Record account balances as at the date of transfer | The transferring entity should download FMIS data (including accounts payable and accounts receivable data) for the transferring function the day after the MoG change is announced, or as soon as practical. |  | CFO Group - transferring entity
5.07 | Information technology | Central Budget Management System (CBMS) | Record account balances as at the date of transfer | Entities transferring functions should download CBMS data for the transferring function the day after the MoG change is announced, or as soon as practical. |  | CFO Group - transferring entity
5.08 | Information technology | Central Budget Management System (CBMS) | Program, outcome, sub-function and appropriation changes | Fill in CBMS Reference Data Structures Workbook for program, outcome, sub-function and appropriation changes in CBMS and return the workbook to Finance. |  | CFO Group - both entities
5.09 | Information technology | Central Budget Management System (CBMS) | Third party access | Prepare third party access forms for CBMS and provide to Finance if required. |  | CFO Group - both entities
5.1 | Information technology | Central Budget Management System (CBMS) | Program, outcome, sub-function and appropriation changes | Consult the CBMS team in Finance to ensure programs/outcomes has been mapped correctly. |  | CFO Group - both entities
5.11 | Information technology | Central Budget Management System (CBMS) | Update estimates | Following CBMS structural changes enter adjustments into CBMS to reflect the change (budget estimates and monthly profile estimates). |  | CFO Group - both entities
5.12 | Information technology | Financial Management Information System (FMIS) Data | Confirm basis of calculation for opening balances | Key balance sheet items to note: -Obtain full list of all employees and leave balances as at date of transfer – discuss with HR to agree date of receipt -Prepayment schedules -Provision for doubtful debts calculations and details of any possible write offs -Loan schedules -Lease schedules -Other long term liabilities -Fixed asset listings - Net Book Value to be transferred -Protocols for payment of payables outstanding at AAO date – will require a full list of accounts payable -Obtain details of cost recovery arrangements. |  | CFO Group - both entities
5.13 | Information technology | Security assessment | Risk assessment | Undertake security assessment for function transferring in. |  | IT Services - receiving entity
5.14 | Information technology | Security assessment | Remedial action | Undertake remedial action to address security concerns as required. |  | IT Services - receiving entity
5.15 | Information technology | Systems Access | Network access | Identify access required by transferring employees. |  | IT Services - receiving entity
5.16 | Information technology | Systems Access | Network access | Set up new user accounts and drive access for transferring employees and provide access to corporate systems such as HR and PDMS. |  | IT Services - receiving entity
5.17 | Information technology | Systems Access | Network access | Deactivate user accounts for transferred employees. |  | IT Services - transferring entity
5.18 | Information technology | Systems Access | Network access | Set up new HR system access and assign supervisors for transferring employees in HR systems. |  | IT Services - receiving entity
5.19 | Information technology | Systems Access | Templates | Update entity templates to reflect the transfer of function. |  | IT Services - both entities
5.2 | Information technology | Financial Management Information System (FMIS) Data | Chart of Accounts | Update the chart of accounts to reflect the transfer of function. |  | CFO Group - receiving entity | bar: 61 to 65
5.21 | Information technology | Financial Management Information System (FMIS) Data | Upload assets and liabilities balances | Following agreement from CFOs on net assets transferring (task no. 10.17), map assets and liabilities balances to general ledger codes and upload balances. |  | CFO Group - receiving entity
5.22 | Information technology | Financial Management Information System (FMIS) Data | Upload assets and liabilities balances | Reconcile uploaded assets and liabilities balances with supporting documentation. |  | CFO Group - receiving entity
5.23 | Information technology | Financial Management Information System (FMIS) Data | Upload assets and liabilities balances | Adjust assets and liabilities balances for any differences in accounting policies between the receiving and transferring entity. |  | CFO Group - receiving entity | bar: 61 to 65
5.24 | Information technology | Financial Management Information System (FMIS) Data | Update subsidiary FMIS modules | Update subsidiary FMIS modules (including accounts payable, accounts receivable, human resources and fixed assets modules) for the transfer of net assets. |  | CFO Group - receiving entity | bar: 61 to 65
5.25 | Information technology | Financial Management Information System (FMIS) Data | Commitments | Record details of any outstanding purchase orders transferring with the transferring function. |  | CFO Group - receiving entity | bar: 61 to 65
5.26 | Information technology | Financial Management Information System (FMIS) Data | Commitments | Cancel any outstanding purchase orders transferring with the transferring function. |  | CFO Group - transferring entity | bar: 61 to 65
5.27 | Information technology | Grants Hub | Update Grants Management Systems | Update grants management systems for transferring grants programs if appropriate. |  | CFO Group - both entities | bar: 61 to 65
5.28 | Information technology | Human Resources Management Information System (HRMIS) Data | Update payroll system for transferring employees | Update payroll system to include transferring employees' pay structures. |  | Human Resources - receiving entity | bar: 61 to 65
5.29 | Information technology | Human Resources Management Information System (HRMIS) Data | Update payroll system for transferring employees | Update payroll system for transferring employees' fortnightly payment details. |  | Human Resources - both entities | bar: 61 to 65
5.3 | Information technology | Human Resources Management Information System (HRMIS) Data | Update HR system for transferring employees | Update HR system to reflect changes to the organisational structure. |  | Human Resources - both entities
5.31 | Information technology | Human Resources Management Information System (HRMIS) Data | Update HR system for transferring employees | Update HR system for transferring employees' leave balances. |  | Human Resources - both entities | bar: 61 to 65
5.32 | Information technology | Business systems | Reconcile supporting systems and modules | Reconcile supporting systems and modules to opening balances and supporting documentation. |  | CFO Group - both entities
5.33 | Information technology | Corporate communications | Update corporate directory | Update corporate directory and phone lists to reflect transferred function. |  | Human Resources - both entities | bar: 61 to 65
5.34 | Information technology | Financial Management Information System (FMIS) Data | Internal budgets | Update organisational structure (and cost centres) to reflect transferred function. |  | CFO Group - both entities | bar: 61 to 65
5.35 | Information technology | Financial Management Information System (FMIS) Data | Internal reporting | Update internal budget allocations and reporting templates to reflect transfer of affected function. |  | CFO Group - both entities | bar: 61 to 65
6 | Average Staffing Level (ASL) | ASL | Employee list | Confirm full list of employees transferring. |  | Human Resources - transferring entity
6.01 | Average Staffing Level (ASL) | ASL | ASL | Calculate the value of ASL to transfer across the forward estimates. |  | CFO Group - transferring entity
6.02 | Average Staffing Level (ASL) | ASL | ASL | Agree the number of ASL to transfer. |  | CFOs - both entities
6.03 | Average Staffing Level (ASL) | ASL | ASL | Advise the relevant AAUs of the ASL to transfer. |  | CFO Group - both entities
7 | Annual appropriations to be transferred | Annual appropriations | Reporting | Prepare detailed appropriation reconciliation as at MoG change date of effect. |  | CFO Group - both entities
7.01 | Annual appropriations to be transferred | Annual appropriations | Negotiations | Undertake negotiations of funding to be transferred (including unspent section 74 retained receipts) |  | CFOs - both entities
7.02 | Annual appropriations to be transferred | Annual appropriations | Negotiate the value of cash balances to be transferred | NCEs agree cash balances to be transferred. Return any excess drawdowns back to the OPA (and relevant appropriation) as appropriation repayments. Return any unspent section 74 retained receipts back to the OPA for crediting against most recent departmental appropriation. CCEs should contact the Annual Appropriations team in Finance. |  | CFOs - both entities
7.03 | Annual appropriations to be transferred | Annual appropriations | Agree mechanism for transfer of current year appropriations | Agree current year amounts to be transferred through section 75 or next round of appropriations, and prior year amounts to be transferred through updated estimates at the next estimates update. |  | CFOs - both entities
7.04 | Annual appropriations to be transferred | Annual appropriations | Section 75 transfers | Prepare draft section 75 transfer forms and provide to Finance (for amounts which will not be transferred at the next estimates update). |  | CFOs - both entities
7.05 | Annual appropriations to be transferred | Annual appropriations | Section 75 transfers | CFO signed final section 75 transfer forms provided to Finance. |  | CFOs - both entities
7.06 | Annual appropriations to be transferred | Annual appropriations | Section 75 transfers | Register Section 75 determinations on the Federal Register of Legislation (http://www.legislation.gov.au) |  | Finance
7.07 | Annual appropriations to be transferred | Annual appropriations | Update CBMS Cash Management Module (CM) balances | Following the commencement of the section 75 determination, transfer appropriations in CBMS CM. |  | CFO Group - both entities | bar: 61 to 65
8 | Special appropriations and special accounts | Planning | Scoping the MoG change | Determine which Special Accounts and Special Appropriations are in scope for transfer. |  | MoG Steering Committee
8.01 | Special appropriations and special accounts | Due diligence | Effect of AAO change | Confirm with legal area that the AAO change is sufficient to transfer responsibility for Special Appropriations and Special Accounts. Where a special account needs to be established, repealed or amended, consult Finance for advice. |  | CFO Group - transferring entity
8.02 | Special appropriations and special accounts | Due diligence | Characteristics of special accounts | Confirm any unusual characteristics in the operation of affected Special Accounts. |  | CFO Group - transferring entity
8.03 | Special appropriations and special accounts | Due diligence | Special appropriations and special accounts | Seek AGS and PM&C advice where there is confusion over responsibility for special appropriations/special accounts - may require a reissue of the AAOs or substituted reference order (see below). |  | Corporate - both entities
8.04 | Special appropriations and special accounts | Special appropriations and special accounts | Special accounts | Liaise with OPC and AGS to draft "substituted reference orders" if required for special appropriations or s80 special accounts (those in Acts). |  | Corporate - receiving entity
8.05 | Special appropriations and special accounts | Special appropriations and special accounts | Update CBMS Cash Management Module (CM) balances | Determine year to date spend for special accounts and special appropriations, and liaise with AAU to ensure CM budgets are established for receiving entity and/or third party access relationships are put in place. |  | CFO Group - both entities
8.06 | Special appropriations and special accounts | Special appropriations and special accounts | Estimates Models | Provide copies of estimates models and example journals transferring the budget estimates. |  | CFO Group - transferring entity
9 | Budget documentation | Due diligence | Outstanding costings | Identify costings and budget submissions under development relevant to the transferring function and provide a copy to the receiving entity. |  | CFO Group - transferring entity
9.01 | Budget documentation | Due diligence | Repealed appropriations | Identify any repealed appropriation that requires reappropriation relevant to the transferring function and provide details to the receiving entity. |  | CFO Group - transferring entity
9.02 | Budget documentation | Due diligence | Comeback submissions | Identify comeback submissions relevant to the transferring function and provide a copy to the receiving entity. |  | CFO Group - transferring entity
9.03 | Budget documentation | Due diligence | Election commitments | Identify any election commitments relevant to the transferring function and provide a copy to the receiving entity. |  | CFO Group - transferring entity
9.04 | Budget documentation | Due diligence | PBS/PAES presentation | Identify the presentation of the transferring function in PBS and PAES documents. |  | CFO Group - both entities
9.05 | Budget documentation | Due diligence | Review estimates and budget documentation | Identify and provide a copy of the workings/models that support the budget estimates and budget documentation related to the transferring function and provide a copy to the receiving entity. |  | CFO Group - transferring entity
10 | Agreement for transfer of net assets and other financial transfers | Agreement for transfer of net assets and other financial transfers | Cash balances | NCEs return any excess drawdowns back to the OPA (and relevant appropriation) as appropriation repayments. Return any unspent section 74 retained receipts back to the OPA for crediting against most recent departmental appropriation. CCEs should contact the Annual Appropriations team in Finance. |  | CFOs - both entities
10.01 | Agreement for transfer of net assets and other financial transfers | Agreement for transfer of net assets and other financial transfers | Cash balances | NCEs agree final cash balances to be transferred back to the OPA and receipted as appropriate. CCEs should contact the Annual Appropriations team in Finance. |  | CFOs - both entities
10.02 | Agreement for transfer of net assets and other financial transfers | Liabilities | Employee provisions | Calculation of Employee Provisions (Annual Leave, Long Service Leave, Superannuation). Leave liability reports provided (once section 72 of PS Act determination finalised) and reconcile to list of employees transferring. |  | CFO Group - transferring entity
10.03 | Agreement for transfer of net assets and other financial transfers | Liabilities | Personal leave balances | Agree treatment of personal leave balances. |  | CFOs - both entities
10.04 | Agreement for transfer of net assets and other financial transfers | Commitments | Purchase orders and commitments | Identify outstanding purchase orders and commitments relevant to the transferring function and provide a copy to the receiving entity. |  | CFO Group - transferring entity
10.05 | Agreement for transfer of net assets and other financial transfers | Assets | Prepayments | Identify prepayments relevant to the transferring function and provide a copy to the receiving entity. |  | CFO Group - transferring entity
10.06 | Agreement for transfer of net assets and other financial transfers | Liabilities | Leases | Record the transfer affected lease liabilities and advise lessor. |  | CFO Group - both entities
10.07 | Agreement for transfer of net assets and other financial transfers | Contingent liabilities | Contingent liabilities | Agree on a detailed list of contingent liabilities (including any pending legal actions). |  | CFOs - both entities
10.08 | Agreement for transfer of net assets and other financial transfers | Contingent assets | Contingent assets | Agree on a detailed list of contingent assets (including any pending legal actions). |  | CFOs - both entities
10.09 | Agreement for transfer of net assets and other financial transfers | Assets | Accounts receivable | Agree on a detailed list of receivables to be transferred. |  | CFOs - both entities
10.1 | Agreement for transfer of net assets and other financial transfers | Assets | Accounts receivable | Agree on details of any recovery action in progress. |  | CFOs - both entities
10.11 | Agreement for transfer of net assets and other financial transfers | Assets | Accounts receivable | Details of any possible debt write-offs. |  | CFOs - both entities
10.12 | Agreement for transfer of net assets and other financial transfers | Assets | Accounts receivable | Details of calculation of provision for doubtful debts. |  | CFOs - both entities
10.13 | Agreement for transfer of net assets and other financial transfers | Assets | Depreciable assets | Calculate net book value of assets to be transferred. |  | CFO Group - transferring entity
10.14 | Agreement for transfer of net assets and other financial transfers | Assets | Depreciable assets | Conduct a physical stocktake of assets held or managed by the affected functions. |  | Corporate - both entities
10.15 | Agreement for transfer of net assets and other financial transfers | Assets | Depreciable assets | Provide copies of previous asset valuations and provision calculations to receiving entity. |  | CFO Group - transferring entity
10.16 | Agreement for transfer of net assets and other financial transfers | Assets and Liabilities | Transfer agreement | Prepare transfer agreement of net assets and liabilities. |  | Corporate - both entities
10.17 | Agreement for transfer of net assets and other financial transfers | Assets and Liabilities | Transfer agreement | CFOs approve of net asset transfer agreement. |  | CFOs - both entities
10.18 | Agreement for transfer of net assets and other financial transfers | Assets and Liabilities | Physical assets transfer | Transfer physical assets. |  | Corporate - both entities
11 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Bank accounts | Confirm if new bank accounts are required or need to be transferred/novated. Advise Finance of changes. |  | CFO Group - receiving entity
11.01 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Bank accounts | Establish new bank accounts as appropriate. Advise Finance of changes. |  | CFO Group - receiving entity
11.02 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Third party access | Prepare third party access. |  | CFO Group - receiving entity
11.03 | Bank accounts and credit cards | Bank Accounts & Credit Cards | EFTPOS facilities | Transfer/arrange new EFTPOS facilities. |  | CFOs - both entities
11.04 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Petty cash advice | NCEs return petty cash advances back to the OPA and receipt as appropriate. CCEs should contact the Annual Appropriations team in Finance. |  | CFOs - both entities
11.05 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Bank accounts | Close Departmental bank account (if required). |  | CFO Group - transferring entity
11.06 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Cab charge | Organise cab charge vouchers & create master cab charge register for central administration. |  | CFO Group - receiving entity
11.07 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Credit cards | Agree process to manage credit card arrangements held by transferring employees. Liaise with credit card providers and/or Finance. |  | MoG Steering Committee
11.08 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Credit cards | Cancel credit cards for transferred employees. |  | CFO Group - transferring entity
11.09 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Credit cards | Institute cost recovery arrangements for credit card transactions as appropriate. |  | CFO Group - transferring entity
11.1 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Credit cards | Consider any requirements to revise the Credit Card Accountable Authority Instruction. |  | Corporate - both entities
11.11 | Bank accounts and credit cards | Bank Accounts & Credit Cards | Credit cards | Issue new credit cards/cancel credit cards. |  | CFO Group - receiving entity
12 | Australian Business Number (ABN) and tax issues | ABN | Goods and Services Tax (GST) | Establish/transfer ABN as appropriate. |  | CFO Group - both entities
12.01 | Australian Business Number (ABN) and tax issues | Tax issues | ATO Portal | Apply for access to the ATO portal. |  | CFO Group - receiving entity
12.02 | Australian Business Number (ABN) and tax issues | Tax issues | Reporting | Review Taxation and reporting requirements, e.g. Monthly BAS return, Annual FBT return, TPAR. |  | CFO Group - both entities
12.03 | Australian Business Number (ABN) and tax issues | Tax issues | Fringe Benefit Tax (FBT) | FBT motor vehicle odometer readings reported to affected entity. Other FBT arrangements identified for transferring employees, e.g. parking. |  | CFO Group - both entities
12.04 | Australian Business Number (ABN) and tax issues | Tax issues | Goods and Services Tax (GST) | Review existing GST rulings, and/or apply for a new ruling/determination. Consult with the ATO. |  | CFO Group - both entities
12.05 | Australian Business Number (ABN) and tax issues | Tax issues | Goods and Services Tax (GST) | Deductible Gift Recipient (DGR) notification and the Deferred GST Scheme documentation. |  | CFO Group - both entities
12.06 | Australian Business Number (ABN) and tax issues | Tax issues | Fringe Benefit Tax (FBT) | Agree reporting of GST, tax, accruals etc. Determine any fleet or pooled vehicle arrangements. Determine if there are any other outstanding taxation matters. |  | CFO Group - both entities
12.07 | Australian Business Number (ABN) and tax issues | Tax issues | Tax rulings | Obtain copies of any tax rulings on tax obligations relating to functions being transferred, or if required, seek new advice. |  | CFO Group - receiving entity
12.08 | Australian Business Number (ABN) and tax issues | Tax issues | Taxable Payment Annual Report (TPAR) | Agree reporting of grants and other taxable payments. |  | CFO Group - both entities
13 | Procurement, contracts and commitments | Procurement, contracts and commitments | Outstanding purchase orders | Determine if outstanding purchase orders relating to the transferring function will transfer to the receiving entity or be voided and re-issued. |  | MoG Steering Committee
13.01 | Procurement, contracts and commitments | Procurement, contracts and commitments | Planned procurement activities | Determine whether any procurement activities currently under way will transfer with the transferring function. |  | MoG Steering Committee
13.02 | Procurement, contracts and commitments | Procurement, contacts and commitments | Ongoing contracts | Transfer operational contracts and advise service providers of the transfer. |  | Procurement or Contract Management - both entities
13.03 | Procurement, contracts and commitments | Procurement, contacts and commitments | Ongoing contracts | Update relevant database or registers for the transfer of ongoing contracts. |  | Procurement or Contract Management - both entities
13.04 | Procurement, contracts and commitments | Procurement, contacts and commitments | Ongoing lease agreements | Update relevant database or registers for the transfer of ongoing lease agreements that transfer with the transferring function. |  | Procurement or Contract Management - both entities
13.05 | Procurement, contracts and commitments | Procurement, contacts and commitments | Commitments | Update relevant database or registers for the transfer of any other commitments that transfer with the transferring function. |  | Procurement or Contract Management - both entities
13.06 | Procurement, contracts and commitments | Procurement, contacts and commitments | Contingent liabilities | Update relevant database or registers for the transfer of any contingent liabilities that transfer with the transferring function. |  | Procurement or Contract Management - both entities
13.07 | Procurement, contracts and commitments | Procurement, contacts and commitments | Transition | Determine how payments for contracts will be made during systems migration. |  | Procurement or Contract Management - both entities
13.08 | Procurement, contracts and commitments | Procurement, contacts and commitments | AusTender | Update AusTender for transfer of function. |  | Procurement or Contract Management - both entities
14 | Financial statements | Planning | Risk analysis | Undertake risk analysis to identify the impact of the MoG change on the financial statements preparation process. |  | CFO Group - both entities
14.01 | Financial statements | Planning | Planning | Update the financial statement preparation plan for the impacts of the MoG change. Contact Finance for advice on disclosure requirements if required. |  | CFO Group - both entities
14.02 | Financial statements | Financial statements | Body of financial statements | Report on transferred functions in the financial statements . |  | CFO Group - both entities
14.03 | Financial statements | Financial statements | Restructure note | Prepare restructure note (or significant event after balance date) to reflect the impact of the MoG change. |  | CFO Group - both entities
14.04 | Financial statements | Financial statements | Appropriation reconciliation | Prepare a detailed appropriation reconciliation as at date of MoG change to include with year end work papers. |  | CFO Group - both entities
14.05 | Financial statements | Financial statements | Executive remuneration note | Document the impact on the executive remuneration note of the impact of the MoG change. |  | CFO Group - both entities
15 | Comcover, Comcare, and superannuation | Insurance | Amend insurance coverage | Advise Comcare and Comcover of the impact of the MoG change on employee levels and operations so insurance coverage and premiums can be amended, and workers compensations/insurance claims can be transferred to the receiving entity |  | Corporate - both entities
15.01 | Comcover, Comcare, and superannuation | Superannuation | Superannuation requirements | Contact Finance to discuss superannuation scheme requirements. |  | Corporate - both entities
16 | Asset management | Stocktake of assets | Stocktake of assets | Conduct stocktake of transferring assets (including property, records, IT equipment) before transfer. |  | Corporate - both entities
16.01 | Asset management | Transfer of Assets | Transfer of assets | Physical delivery of assets identified in the stocktake process (including property, records, IT equipment) to the receiving entity. |  | Corporate - both entities
16.02 | Asset management | Stocktake of assets | Stocktake of assets | Barcode assets transferred and update assets register after transfer. |  | Corporate - both entities
16.03 | Asset management | Update assets register | Update assets register | Reconcile transferred assets with asset balances transferred. |  | CFO Group - both entities
16.04 | Asset management | Update assets register | Update assets register | Update portable and attractive assets register. |  | Corporate - both entities
16.05 | Asset management | Revaluation of assets | Revaluation of assets | Assess whether transferring assets should be revalued and revalue if required. |  | CFO Group - receiving entity
16.06 | Asset management | Capital management plan | Capital management plan | Provide updated Capital Management Plan (CMP) to Finance. |  | CFO Group - both entities
17 | Property | Assessment of leasehold capacity | Assessing leasehold capacity | Receiving entity to review occupancy levels to determine whether transferring employees can be accommodated within their existing tenancies and decide if they wish to do so. |  | Corporate - both entities
17.01 | Property | Timeframe for employee relocation | Timeframe for employee relocation | If the receiving entity decides that transferring employees can be accommodated within their existing tenancies, the receiving entity should advise the transferring entity of their intention and agree on a timeframe to relocate employees and any financial contributions that may be required (this may include lease modifications and office refurbishment/fit-out to accommodate essential employee changes). |  | Corporate - both entities
17.02 | Property | Determining new location | Determining new location | If the receiving entity decides not to accommodate transferring employees within their existing tenancies, they should engage with your entity's property services provider and Property and Construction Division in Finance and advise the transferring entity of their intention and timeframes to relocate employees. |  | Corporate - both entities
17.03 | Property | Employee relocation | Employee relocation | Relocate employees to receiving entities' premises. |  | Corporate - both entities
17.04 | Property | Negotiations | Negotiate sublease or transfer of lease | If the receiving and transferring entity agree that transferring employees should remain located in a tenancy leased by the transferring entity, the receiving and transferring entity should negotiate and enter into a sublease, or transfer of the lease. Advise the lessor where required. |  | Corporate - both entities
17.05 | Property | Excess lease space | Excess lease space | Determine whether the transferring entity will be left with excess lease space. |  | Property - transferring entity
17.06 | Property | Excess lease space | Excess lease space | Contact Finance to determine the most appropriate solution to mange excess lease space if required. |  | Property - transferring entity
18 | Official passports | Negotiations | Transfer of official passports | Agree on a process to transfer official passports held by employees identified to transfer. |  | MoG Steering Committee
18.01 | Official passports | Official passports | Transfer of official passports | Transfer official passports held by employees identified to transfer. |  | Corporate - both entities
18.02 | Official passports | Official passports | Details of official passports | Record the details of the official passports transferred. |  | Corporate - receiving entity
18.03 | Official passports | Official passports | Details of official passports | Advise the Department of Foreign Affairs and Trade of the official passports transferred. |  | Corporate - receiving entity
19 | Information management | Negotiations | Transfer of records | Agree a methodology for the transfer of records. |  | MoG Steering Committee
19.01 | Information management | Information management | Transfer of information assets | Agree on which information assets should be transferred (including personnel records) or duplicated. |  | MoG Steering Committee
19.02 | Information management | Information management | Transfer of information assets | Transfer information assets. |  | Corporate - both entities
19.03 | Information management | Information management | Details of information assets | Update information asset holdings to reflect the transfer of records. |  | Corporate - receiving entity
19.04 | Information management | Subscriptions | Review of subscriptions | Review departmental subscriptions relevant to the transferred function. |  | Corporate - both entities
19.05 | Information management | Subscriptions | Review of subscriptions | Cancel or review departmental subscriptions relevant to the transferred function as appropriate. |  | Corporate - both entities
19.06 | Information management | Information management | Archival of websites and online materials | Ensure legacy websites are archived and previous publications remain accessible. |  | Corporate - both entities
20 | Grants Hub | Grants Hub | Contact service provider | Advise Grants Hub provider of the impact of the MoG change. |  | Corporate - both entities
20.01 | Grants Hub | Negotiations | Renegotiate Grants Hub MOU | Renegotiate Grants Hub MoU if required. |  | Corporate - both entities
20.02 | Grants Hub | Grants Hub | GrantsConnect | Update GrantsConnect for transfer of function. |  | Corporate - both entities
21 | Post-MoG | Evaluation | Post-MoG Review | Conduct a post-MoG change review to ensure all matters have been satisfactorily resolved and compile lessons learnt. |  | Agency Heads - both entities